MULTIDIMENSIONAL TREATMENT FOSTER CARE IN ENGLAND (MTFCE)

PROJECT REPORT

JUNE 2005

Rosemarie Roberts

Project Manager

National MTFCE Team

| CONTENTS | Page Number |
| --- | --- |
| Summary | 1 |
| 1. The Role of the National Team | 4 |
| 2. Site Progress, Successes and Challenges 1. Round One 2. Round Two 3. Round Three 4. Round Four | 4 4 5 5 5 |
| 3. Children in MTFCE Placements 1. Children & Young People in MTFCE Placements as at June 2005 (Fig. 1) 2. Early leavers 3. Gender and Ethnicity 4. Success Factors 5. Tracking Behaviour 6. Example of PDR Graph Showing Reduction in Behaviour Problems over Seven Months (Fig. 2) 7. Comparative Costs | 6 6 6 7 7 8 9 10 |
| 4. Development Plan and Project Timetable 1. Phase One 2. Project Team Development & Timetable for Phase One (Fig. 3) 3. Phase Two 4. Phase Three 5. Planning for the Future 6. MTFCE Project Timetable – showing Site Consultant involvement (Fig. 4) | 10 10 11 12 12 12 15 |
| 5. Development of MTFCE Training Programme 1. Induction Day Numbers Attending introduction to MTFCE Model – Induction Day (Fig. 5) 2. Progress, Networking and Update Days Numbers Attending Progress, Networking and Update Days (Fig. 6) 3. Assessment 4. The MTFCE Model Numbers of Clinical Team Staff Trained in the MTFCE Model (Fig.7) 5. Foster Carer Training Number of Foster Carers Trained (Fig. 8) 6. Other Training Additional Training Modules (Fig.9) | 15 15 15 15 16 16 18 18 18 20 21 21 |
| 6. Evaluation and Audit | 22 |
| 7. Consultation with Oregon Social Learning Center (OSLC) | 22 |
| 8. Intensive Fostering | 22 |
| 9. The Learning So Far | 23 |
| 10. Current Challenges and Aims for the Next Year | 24 |
| Conclusion | 26 |
| Appendix 1 Project staffing Appendix 2 The Points and Levels System | 27 28 |

Summary

The Multidimensional Treatment Foster Care in England (MTFCE) Programme has been established by the Department for Education and Skills (DfES) through a pump-priming grant to local multi-agency teams across England to set up and evaluate a specific evidence-based programme, developed in the USA, for looked after children and young people aged 10 to 16 years.

The impetus for such a programme reflects the considerable concerns regarding poor outcomes for looked after children in England. As a group they are more troubled than others; up to 70% of looked after teenagers have psychiatric disorders compared with 10% living at home (McCann et al 1996, Meltzer 2000); two thirds are reported to have at least one physical complaint (Meltzer et al 2003) and their life chances are considerably poorer.  About two-thirds (63% in 2001) leave school with no formal qualifications, perhaps not surprising in view of the fact that up to 30% are out of mainstream education through exclusion or truancy (Social Exclusion Unit 1998); repeated change of schools is common, not only due to difficulties experienced there, but also due to foster care moves (Morgan 1999).  Crime is also common – 38% of young prisoners had been looked after (Social Services Inspectorate 1997).  Children at the greatest risk are those who have more than one placement disruption and stable placements are linked to positive outcomes, especially in respect to relationship skills, good education, and employment outcomes (Koprowska & Stein 2000).

There have been over 40 published studies of a range of interventions to improve foster care, (reviewed by Reddy and Pfeiffer (1997), the most promising of which has been the Multidimensional Treatment Foster Care (MTFC) model devised by Chamberlain and colleagues at the Oregon Social Learning Centre (OSLC). This model, based on social learning and systemic theory provides a wrap-around, multi-level intervention for young people who are placed as single placements in the foster home. The programme aims to provide the young person with a secure base, systematic responses to their behaviour, opportunities to develop normative and pro-social behaviours, opportunities for improved relationships with their families and increased problem-solving, academic and relationship development skills. The multi-agency team includes the foster carers, programme supervisor, programme manager, birth family therapist, foster carer recruiter/supporter, individual therapist, skills trainer, and education staff. The young person is closely supervised and mentored by the foster carer who administers a points programme guided by the programme supervisor, linked to positive reinforcement, sensitive contingent responding and increased levels of rewards and autonomy. The young person is additionally provided with an individual therapist and skills trainer to aid development of emotional regulation and social skills. A birth family therapist works closely with the family of origin to help resolve relationship and management issues and facilitate contact where possible.

Eight randomised trials and other studies have provided evidence of the effectiveness of MTFC. The first studies explored the feasibility and cost effectiveness of using the model for adolescents referred for delinquency and for children and adolescents leaving the state mental hospital. (Chamberlain & Reid 1991,1998). The evaluations show a greater reduction of offending behaviour and psychological symptoms in children and young people offered treatment foster care compared with treatment as usual. In addition, compared to alternative residential treatment models, the cost of MTFC was substantially lower. Aos et al (1999) calculated that for the young offenders treated, treatment foster care saved 14 US dollars for every dollar spent, making it the most cost-effective intervention studied.

Later studies have examined immediate and long-term outcomes in several areas including: criminal and violent behaviour, young people with behavioural and mental health problems, attachment to caregivers, gender differences, and interventions with younger children  The research has demonstrated positive outcomes for MTFC in all these areas; for example with fewer re-arrests and violent criminal activity and absconding rates for both adolescent boys and girls, lower rates of permanent placement breakdown, lower rates of child behaviour problems and more frequent reunifications with birth families and greater foster carer retention and satisfaction. (Chamberlain et al 1998, Fisher, 1999, 2005)

The introduction of an evidence-based, multi-agency wrap-around service is a significant development in government strategy for vulnerable looked after children and adolescents and many councils nationally have competed for the pump-priming funding. The Multidimensional Treatment Foster Care in England (MTFCE) project began in 2002 when 6 teams, Dorset, Durham, Solihull, Surrey, Wandsworth and Wirral successfully bid for funding.  Surrey subsequently withdrew from the programme due to difficulties in recruiting foster carers and severe budgetary pressures. To the 5 first round teams have been added a further 4 second round teams in Cheshire, Dudley, Kent and Southampton and six third round teams in Gateshead, Hammersmith and Fulham, Northumberland and North Tyneside, North Yorkshire, Reading and South Gloucestershire, making a current total of fifteen teams spread across the country. The selection of the fourth round is currently being considered.

A further innovation has been the introduction of a National Team, based at the Maudsley Hospital in London and Booth Hall Children’s hospital in Manchester. The team was established in order to ensure consistency of approach and fidelity – both key determinants of good outcomes in service development. The National Team provides developmental support, consultancy, training and monitoring and guidance with regard to the MTFCE model. The team receives regular weekly consultation from the programme designers at the Oregon Social Learning Center in the USA.

The MTFCE programme has reached a critical and exciting stage and is beginning to acquire knowledge and experience about the benefits and challenges of setting up an evidence-based multi-agency programme for looked after young people in England.  There are currently 15 sites at various stages of development, 7 of which have children and young people in placement. The first child was admitted to the programme in April 2004 and there are 21 children and young people currently in foster placements.

The project teams have had many successes and have gained experience of the details and intricacies of running the “points and levels” programmes (see Appendix 2), managing the specific behavioural challenges of the children and young people and supporting the foster carers in their task. The project teams have also experienced a number of challenges including; issues of finance, sustainability and commitment of the multi-agency partnerships; recruitment of foster carers and staff and considerations of consent of the children and their families to entering the programme. However, the early indications are that the programme is able to make a significant positive difference to children’s lives, and that children show improvements in behaviour, in their relationships with birth families, with other adults and with peers and greater stability in education.

This report provides an update of project development and activity across the national sites, outlines the progress and developmental plan for the sites, the development of the training programmes for the clinical staff and foster carers and the successes, challenges and learning so far.

References

Aos S, Phipps P, Barnoski R & Lieb R (1999) The comparative costs and benefits of programs to reduce crime: A review of national research findings with implications for Washington state.  Olympia, WA: Washington State Institute for Public Policy.

Chamberlain, P., & Mihalic, S. F. (1998). Multidimensional Treatment Foster Care. In D. S. Elliott (Series Ed.), Book eight: Blueprints for violence prevention. Boulder: Institute of Behavioral Science, University of Colorado at Boulder.

Chamberlain P & Reid JB (1991) Using a specialised foster care treatment model for children and adolescents leaving the state mental hospital.  Journal of Community Psychology, 19, 266-276.

Chamberlain P & Reid JB (1998) Comparison of two community alternatives to incarceration for chronic juvenile offenders.  Journal of Consulting and Clinical Psychology, 66, 624-633.

Fisher, P. A., Burraston, B., & Pears, K. (2005). The Early Intervention Foster Care program: Permanent placement outcomes from a randomized trial. Child Maltreatment, 10, 61-71.

Fisher, P. A., Ellis, B. H., & Chamberlain, P. (1999). Early intervention foster care: A model for preventing risk in young children who have been maltreated. Children services: Social policy, research, and practice, 2(3), 159-182.

Koprowska J & Stein M (2000) The Mental Health of ‘Looked-after’ Young People.  In P Aggleton, J Hurry & I Warwick (eds) Young People and Mental Health. London: John Wiley & Sons Ltd.

McCann JB, James A, Wilson S et al (1996) Prevalence of psychiatric disorders in young people in the care system.  British Medical Journal, 313, 1529-1530.

Meltzer H, Gatwood R, Goodman R et al (2000) Mental Health of Children and Adolescents in Great Britain.  London: The Stationery Office.

Meltzer H, Corbin T, Gatward R, Goodman R, Ford T (2003) The mental health of young people looked after by local authorities in England. Office for National Statistics, London.

Morgan S (1999) Care about Education: A Joint Training Curriculum for Supporting Children in Public Care.  London: National Children’s Bureau.

Reddy LA & Pfeiffer SI (1997) Effectiveness of treatment foster care with children and adolescents: A review of outcome studies.  Journal of the American Academy of Child and Adolescent Psychiatry, 36, 581-588.

Social Exclusion Unit (1998) Truancy and School Exclusion.  London: HMSO.

Social Services Inspectorate (1997) When Leaving Home is Also Leaving Care: An Inspection of Services for Young People Leaving Care. (CI(07)4.  London: Department of Health.

- The Role of the National Team

Evidence from a number of trials concludes that treatment fidelity is a major determinant of outcome. The National Team was commissioned to provide this consistency of training and fidelity to the model in order to ensure the best possible outcomes for the children, young people and their families involved in this innovative project. The Project Director, Dr Stephen Scott, Reader in Child Health at the Institute of Psychiatry, and Child and Adolescent Psychiatrist at the Maudsley Hospital, London, is a leader in the field of conduct disorder and parenting in the UK and has many publications of clinical trials in this area. The rest of the team at the Maudsley and Booth Hall Children’s Hospital in Manchester are family therapists, clinical psychologists and social workers with experience in health, social care, education and offender services and bring a great deal of knowledge, experience and expertise to the programme. The original task of training and ensuring treatment fidelity has developed into a comprehensive management role incorporating; close site consultancy from the development stage to approximately one year post first placements; specific training in the MTFCE model (both alongside staff at the Oregon Social Learning Center and separately); plus a programme of additional training for clinical staff.

The National Team provides ongoing weekly direct clinical consultation and support in the treatment model to the clinical teams, support for local and national evaluation and monitoring and guidance with regard to model adherence. This innovative method of project management includes formal reviews and feedback to the project teams, live and video supervision and written feedback to ensure the teams are given optimum support in taking the programme forward. The National Team’s staffing has this year expanded to include two and a half full-time equivalents in Manchester, in addition to the three and a half full-time equivalent existing staff members in London. This has meant we have been able to continue to provide an appropriate level of support, supervision and training to the current sites.

###### 2. Site Progress, Successes and Challenges

The MTFCE programme has awarded start-up funding to 15 project sites to date and 3 more are due to be funded this year. All 5 of the first round teams and 2 of the second round teams have children in foster care placements, a total of 21 children and young people over 7 sites across England.

Round One

The initial 6 first round teams were awarded their start up grants in 2003. However, the National Training and Consultation Team were not fully employed until the appointment of the National Project Manager in September that year. Consequently, the core training for the clinical teams and foster carers was provided between November 2003 and March 2004, when Oregon Social Learning Center staff came over from the USA to provide training alongside the National Team.

The critical path of each site has been markedly different, with some experiencing more difficulties in becoming established and progressing more slowly than others. One site withdrew from the programme at an early stage due to severe difficulties in recruiting foster carers and concerns regarding sustainability, leaving 5 first round teams in operation.

Three of the first round sites have made excellent progress over the last year and now have well-established teams of foster carers and each has between 4 and 6 children in stable placements. These teams were particularly successful in their initial recruitment of foster carers and have also added more carers into the existing group thereby enhancing its stability. Staff across all agencies have worked extremely hard and with dedication and enthusiasm. The teams are faithfully and successfully applying the MTFCE model and are seeing positive outcomes for the children placed, some of whom have now been in stable placements for over a year.

Two of the first round teams have experienced some difficulties in recruiting and retaining carers. One has lacked crucial staff members, including a permanent Programme Supervisor and a Foster Carer Recruiter and both have only 1 child currently in treatment foster care. This has placed great pressure on the teams’ viability and sustainability. It is to their credit that despite these difficulties, both teams are committed to continuing with the programme and are beginning to successfully recruit new staff and foster carers.

Round Two

Two of the 4 second round teams have children placed and are in the process of recruiting and training more foster carers including respite carers. The 2 remaining teams are at very different stages. One has successfully recruited key members of the clinical team and 5 sets of foster carers and will be ready to place once the foster carers have received the MTFC training from the National Team.

The fourth round 2 site has been delayed due to a complex combination of political and personnel changes at a very senior level. They now have permission to go ahead and are advertising for staff and carers. It is hoped that their critical path will converge with the developing round three sites.

Round Three

Six teams were awarded start up funding in the autumn of 2004. All are beginning to advertise to recruit clinical staff and foster carers and to work on their protocols, financial and sustainability plans. National training is scheduled for September (clinical teams) and October and March (foster carers). Oregon Social Learning Center will be joining the National Team for the first and last of these dates.

Round Four

The fourth round selection is currently being confirmed. The inclusion of a further 4 teams in the programme will lead to there being a total of 19 sites across the country, at various stages of development. An induction day facilitated by the Department for Education and Skills and the National Team will be scheduled for the new teams as soon as possible.

3. Children in MTFCE Placements

The first foster placement took place in April 2004 and 33 children and young people, 24 boys and 9 girls, have been admitted to the programme over the last year. Of the 21 children currently in Treatment Foster Care, 3 have now been in the programme for over a year, have made excellent progress and suitable moving on placements are being sought. Five children have been in placement for more than 6 months duration, 8 for more than 3 months, and 5 for less than 3 months (see Figure1 below). For many children this represents a significant change. Most of the children admitted to the programme have experienced multiple placements, some up to 15 changes in the year preceding MTFC placement. It is expected that placement stability will improve further as the project progresses and the learning is assimilated.

Evidence from Oregon Social Learning Center studies shows that there is a positive treatment effect if a child is in a MTFC placement for 3 months or more. Of the 12 children who have left the programme, 2 did so after more than 6 months, 3 after more than 3 months and 7 after less than 3 months.

Figure1.  Children and Young People in MTFCE Placements as at June 2005

Early Leavers

Analysis of these seven early leavers showed that the 3 who left after less than 1 week broke down due to a number of factors including:

# insufficient information regarding the young person’s background and mental

# health difficulties;

# insufficient information to make an effective risk assessment;

- cost pressures to take a child with very complex needs;

- lack of understanding between agencies concerning the aims of the

programme;

- timing of placement for young people previously in secure accommodation;

- matching with carers;

- very strong identification with peer group;

- longstanding poor relationships with adults/ inability to trust adults.

# Young people who stayed less than three months tended to be:

- male;

- in the older age range of 14/15 years;

- more ambivalent about being in a highly structured and supervised environment, particularly if they had previous experience of the freedoms of an unstructured and unlimiting residential unit;

- more likely to have been accommodated and able to persuade their biological families to withdraw them from the programme at an early stage.

However, for example, in the case of one 14 year-old boy who left after just 3 months in treatment foster care, the programme team had built up a sufficiently good relationship with the family to enable a package of aftercare work to be completed which resulted in him remaining at home and in school for the first time in several years.

Gender and Ethnicity

Many more boys than girls have entered the programme, 24 boys compared with only 9 girls. This reflects the gender differences for out of control children nationally. For some teams this appears to reflect the gender split of the referrals, for other teams this difference also reflects the difficulty in engaging girls who appear more likely to refuse to come into a foster placement. The experience of Oregon Social Learning Center and an emerging finding here is that girls enter the programme with more complex difficulties, often with a history of sexual abuse, are more complex to treat and take longer to respond to the programme. The reasons for the current gender imbalance require further investigation and this will be aided by the data collection and project audit.

The majority of children who have come into the programme are White British (31) and two (6%) children are Black British in origin. These figures are in line with the prevalence of ethnic minorities in the UK (9%) but slightly under representative of the looked after population.  Again the developing trend nationally will be monitored through the data collection and project audit.

Success Factors

Factors considered to be contributing towards placement and programme success include:

- the clinical team using the programme model effectively and keeping in role;

- having a full complement of clinical staff with appropriate training;

- teamwork and keeping a sense of humour;

- supporting the foster carers and 24 hour support;

- staying positive with young people and paying attention to the detail of what they are doing;

- engaging and supporting the young person in education;

- obtaining clear consent from the young person and family on entering the programme;

- engaging with and supporting birth family work;

- everyone in the system being clear with the young person why they are coming into the programme, and the nature and expectations of the programme;

- co-operation and ongoing communication between involved professionals throughout the placement.

“Jane” is an example of one young person’s progress through the programme:

In the year prior to MTFCE placement 15 year-old Jane had experienced fifteen placement breakdowns, allegedly due to her challenging behaviours. Jane's mother placed her into care due to behavioural and relational difficulties, and did not wish any further contact with her daughter. Jane's siblings have remained living at home with their mother.

Upon entering the programme Jane presented with very poor hygiene, verbal aggression, physically intimidating behaviour, poor social skills, and no positive peer relationships. Psychiatric history and assessment suggested that she has an autistic spectrum disorder.  Jane is talented musically and academically.

The Programme Supervisor and Birth Family Therapist worked hard with both the foster carer and the birth family building up their skills and confidence in managing Jane’s difficulties and responding consistently and contingently to her behaviour.

A year into the programme, Jane has completed her GCSE's, is relating positively and appropriately to others and enjoys dressing up and having her hair done. Jane recently went on a shopping trip with her birth mother to buy a dress for the school prom. She is no longer considered to have Asperger’s syndrome.

Comments from Children in the programme;

On receiving a positive comment about herself for the first time

“No-one’s ever told me that before” (J aged 15)

Written in a card to the foster parent,

“This is the best placement I’ve had” (B aged 14)

Tracking Behaviour

As part of the programme, the number of children’s problematic behaviours is monitored on a daily basis for every child via a Parent Daily Report (PDR).

Anonymised data from the foster carers is recorded onto an internet website managed by Oregon Social Learning Center and accessible by the programme teams and the National Team. The website allows for the production of reports and graphs on the progress of the children and young people over time and informs the clinical team regarding decisions about the treatment plan on a daily and weekly basis.

The daily telephone call to the foster carers enables difficulties to be monitored and acted upon at a very early stage and successes to be reinforced. The detail and patterns of the young person’s behaviour shown on the PDR is discussed at both the weekly foster carer and clinical team meetings allowing the team to be highly responsive to the needs of the young person and the programme to be individually tailored to each child.

An example of a PDR graph at figure 2 below shows the reduction of problematic behaviours over a period of several months.

Figure 2. Example of PDR Graph Showing Reduction in Behaviour Problems Over Seven Months (note graph shows USA date order).

The number of children and young people receiving this treatment package are small and it is as yet early days in the life of the national programme. However, initial reports are encouraging. Children and young people who have remained in the programme for more than 3 months are reported to be showing significant improvements across several domains; including behaviour, relationships with adults and peers, school attendance, and relationships with biological families.

Given the potential for improved outcomes it is encouraging that almost 80% of children in MTFCE carry on in stable placements for more than 3 months’ duration. As the project teams and foster carers grow and develop skills and experience it is hoped that this stability rate will further increase.

Comparative Costs

All the children entering the programme have a history of complex needs, often accompanied by multiple placement breakdown and may be in high cost placements of more than £150,000 to £200,000 per annum or clearly likely to need a high cost placement in the near future. These figures also do not take account of the additional costs of mental health or education support or the costs associated with contacts with the family of origin, travel costs for social workers and so on which may be considerable.

Multidimensional Treatment Foster care costs substantially less at around £110,000 to £120,000 per child per annum, based on 4 placements plus 1 respite foster care placement, depending on local salary, travel and accommodation costs. A foster carer recruiter/supporter is part of the treatment team and therefore the ongoing costs of assessment and recruitment of foster carers are included (see Appendix 1 for team staffing). This figure reduces to around £87,000 to £90,000 per child based on 7 placements and 1 respite and allowing for increasing 2 part-time staff to full time. The wrap-around nature of the service means that the total costs of intensive 24 hour support for the children and young people, in the placement, at school and in social activities as well as work with their families of origin and/or moving on placements are all included within the programme

Reviews of current residential homes and non-specialist residential care for children and young people with complex needs suggest little in the way of effectiveness. The long-term economic costs of these young people into their twenties and thirties have been estimated at between £500,000 and £2 million per person for extra services in the UK. In contrast evidence regarding this programme in the USA found substantial cost savings over a period of time for this vulnerable group and it is anticipated that MTFCE will also prove cost effective over the longer term.

## 4. Development Plan and Project Timetable

The MTFCE sites are supported to develop in three main phases following their successful application for start up funding.

Phase One

Phase one is the developmental stage (see Figure 3). The multi-agency teams set up steering groups; develop forward financial plans and work on sustainability issues; recruit clinical staff and foster carers, develop literature and information leaflets for foster carers, children, families and referrers and develop protocols referral criteria for the programme.

This stage takes a minimum of 8 months and for some teams much longer, due to the need to negotiate the continuing financing of the posts, and long-term commitment of all agency partners. A named site consultant from the National Team is appointed to each site. The consultant then visits the site every 3 to 4 weeks, meets with staff as they are appointed into post, attends the steering group meetings and offers additional telephone or email consultation during this phase. The site consultant provides developmental advice, support and guidance to steering groups and senior managers on setting up the MTFCE programmes, recruiting staff and foster carers. Template job descriptions for the clinical staff, sample leaflets and consent forms are provided to each site. Consultants may also be available to make presentations to partner agencies, steering groups and PCT’s (alongside programme sites) and sit on interview panels as appropriate.

The clinical teams and foster carers complete the specialist MTFC training prior to placing the first young person in a MTFCE foster care placement The National Team also provides consultation or progress update days to enable the sites to meet other programmes at the same stage, and share ideas problems and solutions.

# Figure 3.  Project Team Development and Time Line for Phase One

## CLINICAL

## TEAM

STEERING

GROUP

FOSTER

CARERS

## TIME	1	2	3	4	5	6	7		8

Month

Phase Two (see Figure 4)

Phase two begins when the clinical team is in place and meeting on a regular basis.  At this stage the foster carers are being recruited, assessed and approved by the local panel and have completed the local “Skills to Foster” course plus the specialist MTFCE 3 day Foster Carer Training course. The clinical team have also completed the MTFCE training. Recruitment of foster carers continues on a rolling programme.

The first referrals of young people are assessed to determine their individual strengths and needs and for suitability for the programme using the assessment protocol developed by the National Team. They are then matched with foster carers and the first placement is made. The National Team site consultant attends each clinical and foster carer meeting (which are also videoed) providing weekly direct clinical consultation and support in the treatment model to the clinical teams. A sample of video recordings will be sent to OSLC for consultation purposes and to ensure model adherence and fidelity.

A series of regular reviews are held to provide written feedback to the teams regarding their progress in utilising the model, current strengths, and areas to target for improvement. A rolling programme of ongoing training is also provided to support clinical team staff and train new foster carers following the local team’s assessment and approval process.

Phase Three

Phase three is the “step-down” stage and begins approximately nine months after the first foster placement is made. The weekly contact visits from the National Team site consultant reduces to fortnightly, then monthly over an agreed period of about three months after which consultancy is offered as needed.  Sites continue to have access to national training and networking days as required.

We anticipate that many teams will be interested in consolidating their programmes by becoming officially certified by Oregon Social Learning Center as a Multidimensional Treatment Foster Care provider and the National Team will support them in attaining this accreditation.

Planning for the Future

Figure 4 shows the development of the project sites and the involvement of the National Team site consultant over the life of the programme.

The sites demonstrate considerable differences in the development time needed to set up the clinical team and recruit and train the foster carers ready for first placements. This is due to a variety of reasons including problems in recruiting sufficient numbers of foster carers or clinical staff, and difficulties in obtaining financial commitment from health and education partners. This has inevitably affected national training timetables, support and consultancy needs. Two of the second round teams will effectively be in the same timeline as the third round teams. If the fourth round have a short developmental time of 8 months, then the programme will have 12 teams simultaneously requiring intensive support during the middle of 2006, which has resource implications for the National Team. If the fourth round sites develop more slowly, as in previous rounds, then they will have less than the one-year post placement support from the National Team which is currently being provided. Plans to meet the continuing consultation and training needs of all the programmes will be carefully monitored over the next year to take account of these issues.

5. Development of MTFCE Training Programmes

In addition to supporting the development and implementation of the model in the sites, the National Team was commissioned to provide training in the MTFCE model in order to ensure consistency of approach and fidelity to the treatment programme. In order to achieve this, core training in the MTFC model has been provided for each round of the programme for clinical staff and foster carers prior to young people being placed in treatment foster care.

Oregon Social Learning Center staff have been invited to London on two occasions to train clinical staff and foster carers in conjunction with the National MTFCE Team. In addition the National Team has provided training in the assessment requirements of the programme.

The National Team aims to provide the following training programme for all new sites awarded start up funding:

Induction Day

This provides an overview of the MTFC model, the research evidence from randomised control trials in the USA, the English programme content, the role of the National team and Department for Education and Skills expectations of the sites (see figure 5.)

Progress, Networking and Update Days

These provide an opportunity for the lead managers to meet with colleagues from other developing sites to network, exchange information concerning common dilemmas and possible solutions and to gain further information about the model e.g. ideas about successful recruitment of foster carers (see figure 6).

Assessment

Once key members of the clinical teams have been recruited, training in the assessment protocol for the programme takes place. This enables the teams to become familiar with the specific measures and assessment templates to aid assessment and planning of the treatment goals for children being considered for the programme. This is an innovation to the original USA programme and takes account of the specific needs of the looked after population in England and ensures that there is a comprehensive and detailed assessment of the child’s strengths and needs prior to entering the MTFCE programme.

The assessment has 2 main functions; clinical and evaluative. Firstly, to provide detailed and specific information to assess the young person’s current mental, physical, psychological, social and educational functioning which will then inform the planning of the treatment goals for each young person coming into MTFCE, including a detailed risk assessment from which careful contingency plans can be made. Secondly, to provide baseline data of the young person’s functioning, strengths and difficulties to enable comparisons to be made across the programme sites. In the case of 1 specific measure - the Development and Well-Being Assessment (DAWBA) - this will enable us to compare the psychiatric status of children in this programme with the large Office for National Statistics (ONS) study funded by the Department of Health on the mental health of children looked after. It is anticipated that the group of children referred to MTFCE will have a higher level of complexity of need, including more mental health difficulties than the general looked after population. Professor Robert Goodman who designed the measure has agreed to rate all the DAWBA’s and provide formal diagnostic reports to the clinical teams within a short time period. The baseline measures are as follows;

| Measure | Completed by | Information Gained |
| --- | --- | --- |
| Strengths & Difficulties Questionnaire (SDQ) | Child, recent carer, teacher | Brief behavioural screening questionnaire for emotional, conduct hyperactivity and peer group difficulties plus pro-social behaviour |
| Development and Well-Being Assessment (DAWBA) | Child (aged 11-17), recent carer or parent, teacher | Provides ICD-10 and DSM-IV psychiatric diagnoses on 5-17 year olds. The DAWBA primarily focuses on the common emotional, behavioural and hyperactivity disorders, though it does cover less common disorders more briefly. |
| Children’s Global Assessment Scale (C-GAS) | Recent carer, teacher, social worker | 100-point rating scale measuring psychological, social and school functioning for children aged 6-17. Valid and reliable tool for rating a child's general level of functioning on a health-illness continuum. |
| Weschler Intelligence Scale for Children (WISC) | Child | Used for measuring intelligence (IQ). Up to 12 sub-tests are usually administered; some provide the performance IQ, some the verbal IQ. A full-scale IQ is achieved from these figures. The individual sub-tests indicate strengths and weaknesses in the performance of the subject. This test can only be administered by an educational psychologist. |
| Weschler objective reading dimensions test (WORD) | Child | Measures reading accuracy and reading comprehension scores |

The assessment begins the process of engaging and familiarising the young person and birth/adoptive or extended family with the programme aims, philosophy and staff and provides basic data which can be used for both local and national evaluation. The assessment of the family of origin begins at the point when the programme team are engaging the child and family to obtain consent to their child coming into the programme. This assessment is not a single event but a process which takes place over a period of time and informs the team about the families’ ability to support the placement and work with the programme to attempt to improve relationships and understanding between themselves and their child, whether or not the plan is for the child to return home. Where the child has some contact with their birth family, engagement with the clinical team may be crucial in assisting the child to successfully engage and work with the MTFCE programme.

The educational assessment provides vital information to the clinical team and the prospective school or educational placement in understanding the child’s strengths and needs. This is a particularly important area for looked after children nationally who are particularly at risk of poor educational attainments. About two-thirds (63% in 2001) have no formal qualifications, up to 30% are out of mainstream education through exclusion or truancy, repeated change of schools is common, not only due to difficulties experienced there, but also due to foster care moves.  They may also have had inadequate prior assessment and identification of their educational needs. The aim of the MTFCE programmes is for all children to have a school or educational place which is negotiated and intensively supported by the educational specialist on the MTFCE clinical team and is a core part of the daily points and levels programme.

All the information from interviews, assessment measures, and files is collated into a single document which summarises the child’s strengths, difficulties and needs and any diagnosis. From this formulation the specific and short and long-term treatment goals in relation to the programme are planned and then reviewed and revised on a weekly and sometimes daily basis.

The MTFC Model

Specific training in the core principles, history, philosophy and practice of the MTFC model takes place with the whole clinical team. The training provides the teams with the basic skills and knowledge needed to set up and run the treatment programme for children and young people. The role of each member of the team is differentiated and clearly set out and the operational aspects of the programme outlined. For the first and second round sites, staff from Oregon Social Learning Center have joined the National Team to facilitate this training and this will be repeated for the third round in September of this year. We also hope that clinical staff from the first round will assist in this years training and share their experiences.

Figure 7. Numbers of clinical team staff trained in the MTFCE model

Foster Carer Training

The training for the foster carers takes place once the carers have completed the “Skills to Foster” training provided by the local authority, have been formally assessed and then approved by panel. They then receive the additional 3 days training in the MTFCE model. Similarly to the training for the clinical teams this provides the basic information needed to understand the principles and practice of operating the programme in the foster carers’ home using the points and levels system (see Appendix 2).

For the first and second round sites, foster carer trainers, who are also experienced foster parents from Oregon Social Learning Center, have joined the National Team to facilitate this training and this will be repeated for the third round. In Oregon this training is completed in 2 days.  However, in order to accommodate long travelling distances associated with national training and the differences in legal, philosophical and cultural context in England, the National Team have extended this training to 3 days. The training includes a number of case examples, practice exercises and role plays, information about how attachment theory relates to the behavioural programme and examples of dealing with specific behavioural problems.

Figure 8.  Numbers of Foster Carers Trained

The recruitment of foster carers is a continual process and has not been consistent across the sites. Foster carers have sometimes not been ready to receive the training at the scheduled time. As a result the National Team have made foster carer training available on a rolling programme in order to train carers at reasonable time intervals following their assessments and approval as foster carers. Figure 8 above shows the numbers of foster carers trained either with Oregon Social Learning Center or the National Team only. A total of 70 carers have been trained since the programme began.

The next foster carer training with scheduled for the third round (plus additional carers from earlier rounds who are ready for training) will take place in November 2005 and March 2006.

Other Training

In addition a rolling programme of training/consultation and networking days has been provided by the National Team. General training in the application of social learning theory is open to all clinical staff and has been well attended. Smaller training/consultations have been held to allow individual team members to network, learn from each other and provide ongoing support for their specific roles within the clinical teams. For example the training for skills workers included skills practice and role plays in the community and the education workers day included exploration of the role of the teachers in the MTFCE teams and provided an opportunity to exchange ideas and information and learn from each other.

Figure 9. Additional Training Modules

6. Evaluation and Audit

The independent National Evaluation Team from the universities of Manchester and York was appointed in the autumn of 2004 and has worked closely with the National Team in understanding the structures and systems of the programme sites and determining the practicalities of undertaking a Randomised Controlled Trial (RCT). An information day for the project sites held in December was well attended by senior staff from all the current sites.  Issues raised at this meeting, subsequent site visits and liaison with steering groups by the Evaluation Team have enabled modifications to the final design of the trial. Randomised trials of this nature are not common in social care and while enthusiastic and interested in the potential outcomes programme sites continue to have concerns regarding the randomisation process. However the overall response is predominantly positive and the data collection is due to begin shortly. The National Team will continue to assist the evaluation process and support the teams in resolving specific issues.

Programme sites are also collecting information regarding children and young people placed in the programme and this information is being collated by the National Team for audit purposes. This will provide the national programme and individual teams with general information regarding the status of children entering and leaving MTFCE, including demographic data, numbers of referrals, type and severity of difficulties experienced by the children, their families or previous carers, educational attainment, criminal offences and so on. This information will be accessible in advance of the main evaluation and useful for senior managers and steering groups in beginning to obtain a picture of how the programmes are working, the specific difficulties and issues arising including some indications of the factors contributing to successful placements and treatment outcomes.

7. Consultation with Oregon Social Learning Center

The National Team have continued to work closely with Oregon Social Learning Center and receive weekly clinical telephone consultation with Dr Peter Sprengelmeyer on the operational aspects of the model. Oregon Social Learning Center have also been invited to join with the National Team to deliver training in the MTFC model to clinical team staff and new foster carers.

The contract with Oregon Social Learning Center is currently in the process of being renewed and will include video review of tapes provided by the programme sites of clinical and foster carer meetings for the monitoring of fidelity to the programme and consultation on the consultation provided to the sites by the National Team.

8. Intensive Fostering

In 2004 the Youth Justice Board decided to use the same clinical model with the Intensive Fostering Programme for young offenders serving a community based sentence. The Department for Education and Skills and the National Team are working in close collaboration with their three pilot programmes and are beginning joint training programmes.

9. The Learning So Far

For the phase one developmental stage the feedback from the programme sites is that ongoing work on sustainability, financial forward planning and multi-agency partnerships is crucial. Teams who have experienced changes in senior management personnel, structural reorganisation, political emphasis, or financial imperatives have suffered from delays, involving local authorities in protracted re-negotiations with health and education partners. The lessons learned for the next sites are being passed on via the national network and the National Team. These include ensuring good liaison with signatories, passing on commitment and responsibility for the programme to new managers, ensuring the MTFCE programme is part of CAMHS strategy and is a standing agenda item at the various partnership meetings.

The greatest learning has inevitably come with the teams’ experience of implementing the programme with children and young people in placements. Feedback from one experienced team is that the programme is highly successful if the model is followed very closely and all the team is working together towards the same goals.

Some of the learning has been predictable; for example the need to ensure that there is clear understanding among and consent to the programme from all involved including the child, social worker and birth or adoptive family; to ensure that the whole clinical team is in place before making placements and that careful assessments and contingency plans protect again admission of young people for whom the programme is unsuitable, for example for those with acute mental health needs not easily containable in a community placement.

The following are a sample of comments from programme staff and site consultants regarding their learning in developing the MTFCE programme:

- Consent

- Consent from all parts of the child’s system is crucial, if the young person or birth family are not in agreement then it is very difficult to engage them in the programme.

- The child’s social worker and other agencies need to understand the philosophy of the programme so they don’t undermine it.

- For young people who have had an enormous amount of freedom in residential units or foster care, consent to a programme where they are supervised, escorted to school and not allowed to use their mobile phone is a major issue – the current care system in effect creates a problem.

- Age of Children and Young People

- The younger we can start working with young people and the earlier on their care career, the more effective we are likely to be.

- The younger end of the 10-16 age spectrum respond well to the points and level system and it makes sense to them.

- Work with birth families

- Families need to be engaged from the outset and know how the programme will work with them and their child.

- This (birth family therapist) is the best job on the team – parents who have never co-operated with social services are working with us to help their child have a better relationship with them – even if the plan is not for them to go home.

- School/Education

- Having an experienced teacher on the programme team has been crucial in ensuring that children have educational input – not having a school place puts a great deal of strain on the foster placements.

- A stable school placement supported by the MTFCE programme makes an enormous difference to the child’s experience and self-confidence.

- Explanations to the Young people

- Clear explanations by their social workers about why they are moving into MTFCE is absolutely essential and helps the child to accept and settle in the new placement.

- Everyone in the system needs to be clear with the young person about their behavioural difficulties otherwise it leaves the child thinking that it is only the MTFCE team that thinks there is a problem.

- Respite care

- It is important for the carers to have breaks as the programme is very intense and we ask a lot of them.

- Without respite the carers would not have been able to manage the intensity of the difficulties in the early stages.

- Recruitment of carers

- For the programmes to be successful at an early stage they need to have a minimum of 3 placements plus one respite – that way the carers support each other and the staff quickly gain experience.

- We need to keep up the recruitment campaign even when we have fosters  carers and children in place to ensure against illness, unexpected events and so on.

10. Current Challenges and Aims for the Next Year

The project faces a number of challenges for the Programme Sites and the National Team over the next year. The key issues are as follows;

1. Finance

- Sustainability issues – decisions need to be made at an early stage by senior managers as to whether continuing funding for the programme, once the pump-priming grant ends, is financed out of new monies (for example under Invest to Save) or from existing funding of current provision (e.g. private and voluntary, out of county placements, residential units) or a combination of sources.

- Senior managers may need to work to maintain the financial commitment of partnership agencies, particularly education and health, over the longer term.

- Project teams may need to manage political, ideological and senior personnel changes which directly affect commitment to the programme.

- Teams may need to insist on admitting children and young people into the programme according to established referral criteria, individual need and suitability and resist financial pressures to make savings by taking children and young people solely on the grounds of cost.

- Recruitment and Retention

- Round two and three programmes embarking on the first round of recruitment of foster carers should ideally aim to recruit 4 or 5 sets of competent carers at the outset. This enables several children to be placed at once giving teams and carers the opportunity to learn from experience and from each other and reduces the cost per placement.

- Established programmes with existing carers will need to continue to recruit foster carers to build up numbers to ensure sustainability and allow for turnover.

- Developing and established teams need to recruit and then retain appropriately skilled and experienced clinical team staff.

- Moving on Placements

- Once programmes have children in place consideration needs to be given to where they will be moving on to after the short-term MTFCE placement ends. Finding suitable moving on placements such as long-term less intensive foster care will be a considerable challenge. Several of the first round teams are beginning to think creatively around this issue and this will be an area of development over the next year.

- Evaluation and Audit

- The challenge of ensuring sufficient throughput of potential referrals to support the national evaluation will affect all the teams over the next year. The National Team will aim to support project teams and the independent evaluators in ensuring the national evaluation is managed as smoothly as possible.

- Positive outcome results from the national evaluation will be very helpful to the programme teams in demonstrating value for money and justifying continued investment in the programme. However, results of the evaluation will not be available for some time. In the interim clinical teams will collect information about referrals and placements which will be collated by the National Team to provide information about early outcomes and programme trends.

- Programme Fidelity

- The National Team will need to continue to monitor and support teams to adhere to the MTFCE model in order to secure the best outcomes for children and young people.

- Training and Support

- The National Team will need to ensure that training, networking and developmental needs of all the teams in the programme are met within an appropriate time period and within current resources.

- The development of a MTFCE website will need to be finalised by the National Team.

Conclusion

The MTFCE programme is an important and innovative development in the care of looked after children and young people. The programme’s aims to modernise social care to achieve better life chances and improved outcomes for this vulnerable group of children using an evidence-based model and multi-agency teams creates a major challenge to which the programme sites have risen admirably.

One of the greatest challenges in transferring the American programme to this country has been in managing the philosophical differences between the social learning theory model and current beliefs and practices regarding child care in England. The journey project teams have all taken in absorbing new ideas and developing new systems and practices for multi-agency working has been remarkable. Willingness to accommodate and integrate cultural, philosophical and systemic differences while not compromising the integrity of the model has been evident on both sides of the Atlantic. It is clear that the hard work and dedication of the foster carers and clinical staff in the application of the programme is beginning to demonstrate improvements in children and young people’s functioning across several domains; including behaviour, relationships with adults and peers, school attendance and achievement, and relationships with biological families.

Rosemarie Roberts

Project Manager

National MTFCE Team

# Appendix 1

# MULTIDIMENSIONAL TREATMENT FOSTER CARE in ENGLAND (MTFCE)

PROJECT STAFFING

The MTFC programme developed by the Oregon Social Learning Center in the USA provides clear guidelines for the staffing of the clinical team which is essential for carrying out the treatment programme in the most effective, consistent and coherent way. This is important in order to ensure fidelity to the model and the greatest chance of positive outcomes for the children and young people admitted to the programme.

The multi-agency MTFCE team therefore consists of staff from social services, CAMHS and education to meet these requirements and the requirements of our specific context in England.

MTFCE Staffing Requirements

### Programme Manager

Programme Supervisor

Foster carer Recruiter/Trainer

Birth Family Therapist

Young Person’s Individual Therapist

Skills Trainer

Education personnel e.g. teacher

Psychiatrist (1-2 sessions)

Clinical Psychologist (if not appointed as PS or IT then 1-2 sessions for assessment)

Appendix 2

# The Points and Levels System

During a young person’s MTFCE placement they gradually progress through a 3 level behaviour management system.  This is a structured programme designed to teach pro-social skills, reinforce positive behaviour and attitudes through tangible rewards and offer sanctions for problem behaviour.  The young person earns the right to move up to the next level by earning sufficient points.  Each successive level is characterised by gradual reduction in supervision and an increase in privileges. The aim is to have a young person functioning well within the context of a family by the end of the placement.

Level 1

The young person spends a minimum of 3 weeks at Level 1 when they first enter the placement and are settling in.  At this level they are supervised at all times by their carers, education staff and other MTFCE workers. The focus is on immediate reinforcement for appropriate behaviour. Points are earned easily for routine activities, for example - getting up on time would earn 10 points. Typically, young people earn 100 to 130 points a day. They must accumulate a total of 2100 points to move to Level 2, which most do in about 3 weeks. The points are traded for very basic privileges the following day, for example - watching a TV programme.

Level 2

The treatment team is likely to see the greatest change in the young person’s behaviour during Level 2.  Points earned 1 week are used to buy privileges the next. The young person begins to experience delayed gratification and to develop the capacity to plan ahead. The amount and quality of privileges increases from Level 1 and can continue to increase throughout Level 2 as the young person’s skills improve, offering an opportunity to become increasingly more responsible and confident.

Young people can use points to choose to stay up later, have longer time on the computer, activity time with friends - although the carers and MTFCE team will know where a young person is at any time. They can be demoted to Level 1 for a day if they fail to earn the minimum amount of daily points. The therapist works with the young person to propose new privileges that are of interest to her. She is then coached on how to appropriately ask and negotiate for what she wants. Typically youngsters earn 700 to 900 points per week on Level 2, and stay on this level for 12 to 16 weeks.

Level 3

Level 3 can be considered a maintenance phase.  During this time, young people are expected to maintain their newly learned skills with less structure.  Youngsters have more opportunity to exercise their own judgment and must handle that responsibility reasonably well to stay on this level. The programme supervisor and foster carers use their discretion on this level to customise privileges as well as expected behaviours, being careful to not allow more freedom than the young people can handle, but also being sure they have opportunities to practice appropriate skills and behaviours in more naturalistic settings.  To remain at this level a minimum of 120 points must be earned each day.

Basic privileges no longer need to be earned and encouragement is given to take greater responsibility for their own decision-making and actions.  However, plans for free time must still be approved in advance. Positive achievements and pro-social interactions are consolidated during Level 3. Plans for any aftercare placement are arranged to fit with these achievements to minimise transition difficulties.

# Text boxes

Appoint Project

Manager & Foster

Carer Recruiter

Appoint Programme Supervisor,

Birth Family Therapist & Individual Therapist

Appoint Education.

Support e.g. Specialist Teacher

Appoint

Skills

Trainers

OSLC + National team train Clinical staff in MTFCE model

Identify accommodation

Inter-agency structures in place

Training

for skills trainers

Referrals accepted, YP seen, consents obtained

Individual programme devised

Steering Group set up

Introductory Training plus  Assessment training

Goals & Tasks of Team defined

Assessments of YP, approval & matching

Plan for sustainability

Set up admin procedures – referral criteria, pathways

Agree & sign off JD’s for first posts

Recruitment programme leaflets & posters

Approval by panel

First

Placement

Assessment plus

“Skills to Foster” Course

Telephone interview & home visits

OSLC + National Team train foster carers in MTFCE model

Recruit Foster Carers

<4 week time gap

Continue recruitment of Foster Carers