SCHOOL SUPPORT STAFF NEGOTIATING BODY

INTERIM REPORT TO THE SECRETARY OF STATE ON SSSNB PROGRESS – 1 DECEMBER 2009

SUMMARY

1.	The interim report below provides a general update of progress as required by the Secretary of State’s Referral Letter of 29 July 2009.

2.	Considerable progress has been made in this new area of negotiated but regulated determination of pay and conditions.  In these first five months a good start has been made, with some inevitable issues and challenges still to overcome.

3.	The interim report sets out progress in three areas:

A.	Operation of the Body (paragraphs 7 and 8);

B.	Progress against Referral Letter matters (paragraphs 9 to 25);

C.	SSSNB remit (paragraphs 26 to 31).

4.	Operation of the Body: the three tier structure for managing our business and our meeting frequency is described below (paragraphs 7 and 8).  The Employers’ Side have made clear that the employers they represent are not wholeheartedly in support of the SSSNB process although they continue to participate positively and in good faith.

5.	Referral Letter matters:

(a)	Core Contract – substantial agreement has been reached between Employers and Unions and a draft Core Contract sent out for informal consultation on 6 November 2009.  Feedback is due by 15 December 2009.  Development of the Core Contract has resulted in further discussion of DCSF’s position on SSSNB’s remit.  If the remit is narrowed to exclude the majority of terms and conditions the Core Contract becomes a much more difficult matter to deliver;

(b)	Working Year – there is agreement that there should be a single method to define the Working Year.  However, there is much work to be done on narrowing the gap between the different Employer/Trade Union positions on this matter;

(c)	Job role profiles – considerable progress in agreeing job families and profiles has been achieved.  Under OME’s lead and with full Employer/Union support, external expertise was commissioned to provide consultancy support for Phase 1 of a 3-Phase programme of consultancy and support and funding was approved by the Secretary of State for Phases 1 and 2 (the latter subject to provisos – see paragraph 23);

(d)	Job evaluation – a JE scheme has been broadly agreed, subject to initial testing (of factors and levels) and our consultants’ review by the end of February 2010.  It will be presented to the Full SSSNB for agreement and full testing will take place in Phase 2;

(e)	Implementation strategy – yet to be discussed in detail by SSSNB as further work on the framework is required.  Consultants will provide advice (by end of February 2010) on the first stage of an implementation strategy (covering schedule, costs and resources and issues for managing transition and steady state);

(f)	Other issues – we have:

- Initiated discussions on how the pay and conditions framework can bring about “national consistency and local flexibility”;

- Agreed SSSNB’s information requirements and asked DCSF to address identified information gaps; and

- Agreed a joint approach to communications and the requirement for a communications strategy and detailed plan.

(g)	Factors in the Referral Letter to have regard to – we have been mindful throughout of the 11 factors across all strands of our work (see paragraphs 24-25);

(h)	Progress against the Referral Letter timings:

- The Referral Letter requires the Body to deliver to the Secretary of State “any agreements that it has reached by 28 May 2010”.  As can be seen from this interim report substantial progress has been made but there is still much to do.  Progress towards that date is good.  Eventual success will depend on a smooth passage through some difficult issues particularly the remit, willingness to compromise, and successful testing of role profiles and the job evaluation scheme;

- We also identified that “everything is agreed or nothing is agreed” is an issue to be addressed and this will have a significant bearing on timing and outcomes.

6.	SSSNB remit:

(a)	We have spent a considerable time seeking clarification of our remit.   Both Employers and Trade Unions clearly understood that they had a wide-ranging remit to cover all terms and conditions of support staff to help national consistency and to avoid equal pay claims;

(b)	Development of the Core Contract covering all contractual terms for school support staff (as recommended by BCHR) led to the clear need to establish a School Support Staff Terms and Conditions Handbook to avoid an excessively long and cluttered contract;

(c)	DCSF told us that the statutory remit is worded to mirror that in place for school teachers.  If matters were to arise that fell outside the remit of the SSSNB this should be for the Trade Unions and Employers to decide where and how those matters should be negotiated.  In recent weeks DCSF has informed us that, in their view, the majority of terms and conditions (as defined in the draft Terms and Conditions Handbook) fall outside the remit of SSSNB.  According to the most recent DCSF advice (November 2009), the body’s remit covers only three items in the draft Core Contract: job title, remuneration and working hours.  This message caused serious and unified concern among Employers and Unions and we are still in conversation with DCSF over this matter;

(d)	We await further DCSF comments.  If the remit does exclude the majority of terms and conditions, it raises the question which body should consider the significant number of matters outside the remit; it creates serious difficulties with the Core Contract; it is the strong view of Employers that it introduces significant risk of equal value claims; and it makes movement of support staff away from the local government arena towards its own separate Body increasingly difficult.  The issue is being given high priority by all the parties.

A.	OPERATION OF THE BODY

7.	The Full SSSNB held its inaugural meeting on 7 July 2009.  We agreed a three tier approach to managing our business:

- The Full SSSNB – to hold the decision-making function and direct the Executive Group;

- The Executive Group – to manage the work programme including oversight of working groups and to prepare recommendations or proposals for referral to the Full SSSNB; and

- Working Groups – the first two are (i) the Core Contract and Working Year Working Group and (ii) the Role Profiles and Job Measurement Working Group.

8.	We have held 24 meetings – 3 meetings of the Full SSSNB, 7 meetings of the Executive Group, 7 meetings of the Core Contract and Working Year Working Group, and 7 meetings of the Role Profiles and Job Measurement Working Group.  In conducting our business, the Employers’ Side has made it clear that the employers they represented were not wholeheartedly in support of the SSSNB process although the Employers’ Side continued to participate positively and in good faith.

B.	PROGRESS AGAINST REFERRAL LETTER MATTERS

THE PRODUCTION OF A CORE CONTRACT OF EMPLOYMENT TO COVER REMUNERATION, DUTIES AND WORKING TIME

Core Contract

9.	We have concluded the initial phase of work to produce a draft Core Contract for national application.  The draft contract draws on DCSF’s earlier commissioned research from BCHR.  We reached consensus on all the contract clauses except those key ones covering remuneration and holidays.  These are the subject of separate negotiations.  The draft of the contract includes employer guidance notes and cross-references to local procedures where appropriate.

10.	Our discussions on the Core Contract have also identified the necessity for a new School Support Staff Terms and Conditions Handbook and work has started to identify its content in draft.  This Handbook is central to our discussions on the Body’s remit.  If the remit is narrowed to exclude the majority of terms and conditions, the Core Contract becomes a much more difficult matter to deliver.

11.	The draft contract is currently under informal consultation through SSSNB member organisations (using the Employers’ Side “sounding board” and regional networks, Union national committees, and CofE Directors of Education and secondary heads) – feedback is due by 15 December 2009.  The aim is to agree modifications to the contract and guidance notes and determine the requirements for legal advice in January and February 2010.

12.	Successful progress on this issue is closely linked to clarifying SSSNB’s remit as soon as possible.

Working Year

13.	The definition of the Working Year is a particular concern to the support staff workforce as significant numbers work term time and part time but also many support staff work a longer year.  We have reviewed the two options recommended by BCHR earlier in 2009.  Employers and Trade Unions have undertaken further work and defined their proposed methodologies for calculating the working year.  There is agreement that a single method clearly understandable to the workforce is required to promote consistency.

14.	The Employers’ Side favour application of a consistent methodology based on pro rating from full time working (37 hours per week for 52 weeks).  The Trade Union Side propose that term time working should become the working year drawing on the school teachers’ model.

15.	Under either model, definitions of working days, non-working days and holidays are essential and require legal advice, which is being sought.  The implications for pension entitlements (particularly reckonable service) are also being kept under review.

16.	This area is proving contentious and appreciable negotiation is still required on the two methodologies.  The next step is consideration of the detailed legal advice.

THE DESIGN OF NATIONAL JOB ROLE PROFILES TO COVER CORE SCHOOL SUPPORT STAFF ROLES

17.	We have pooled extensive information on support staff roles to arrive at an agreed list of job families and profiles.  Sources included BCHR’s recommended 61 role profiles, and the roles identified by local authorities, TDA, DISS, the Schools Recruitment Service and DCSF’s Workforce Data Standards.  All SSSNB member organisations were consulted on the coverage.

18.	Detailed discussions agreed five job families and 112 support staff jobs requiring profiles.  The extensive coverage of profiles (which includes different levels of roles) was considered essential to reflect the workforce and to support a matching process under job evaluation – the numbers may be pared back.  Profiles will incorporate occupational standards and apprenticeship requirements.  The agreed list and source data from around 40 local authorities form the basis of our consultants’ work with SSSNB member organisations to develop a national set of role profiles by the end of February 2010.

THE DEVELOPMENT AND PRODUCTION OF A METHOD FOR CONVERTING THOSE JOB ROLE PROFILES INTO A SALARY STRUCTURE (JOB EVALUATION)

19.	In early discussions, we agreed that a bespoke job evaluation system was required and that extensive testing in schools was essential.  We also assessed the key aspects of NHS Agenda for Change.  BCHR’s recommended job evaluation scheme and further technical advice from the Union Side’s job evaluation adviser provided a base for detailed SSSNB discussions.  We have broadly agreed a scheme, which has been initially assessed against an equal pay model but the scheme needs testing in the field.  Our discussions have also highlighted the areas required for initial testing and the extensive testing in Phase 2.

20.	In conjunction with agreeing a set of role profiles, our consultants are reviewing the job evaluation scheme as proposed by SSSNB.  Initial testing of the scheme against the role profiles and “real” jobs from a sample of 15 schools will produce a job evaluation scheme ready for a full testing programme in Phase 2.  The scheme will be presented to SSSNB’s Executive Group by the end of February 2010 for agreement.  We will begin discussions on the pay structure and assimilation early in December 2009.

A STRATEGY THAT WILL EFFECTIVELY IMPLEMENT THE NATIONAL PAY AND CONDITIONS’ FRAMEWORK IN ALL SCHOOLS MAINTAINED BY LOCAL AUTHORITIES IN ENGLAND INCLUDING A METHODOLOGY TO MANAGE BOTH TRANSITION AND THE STEADY STATE

21.	The strategy to manage implementation of a new framework has yet to be discussed in detail by SSSNB, as further work on the framework is required.  However, we have identified the need for accurate data to inform an assessment of implementation costs.

22.	We have asked our consultants to provide advice on the first stage of an implementation strategy.  This will capture an appraisal of our options, consideration of potential providers and the required supporting resources (staff, training and materials).  Our consultants will advise on the schedule for implementation, including the full testing phase, potential costs and issues for managing transition and steady state.  The plan will be presented to SSSNB’s Executive Group by the end of February 2010 and, once agreed by SSSNB, will specifically support the next stage of full testing.

23.	Other issues

(a)	We have agreed a business case for consultancy support in three phases (i) to design and develop a set of national role profiles, a bespoke job evaluation system and an implementation programme (ii) a testing phase and (iii) full implementation.  Funding for Phases 1 and 2 was approved by the Secretary of State on 14 October with provisos on Phase 2.  Phase 2 is subject to the outputs from Phase 1 meeting the requirements of the Referral Letter, meeting the timelines in the business case and reporting on the feasibility of delivering a new system;

(b)	We have commissioned external expertise to undertake the design and development phase with a completion date of 28 February 2010.  The outcomes will inform the testing phase for which procurement and project management arrangements are under discussion.  In view of the continued reservations of the employers they represent, the Employers’ Side decided it would be inappropriate for them to lead on the procurement of Phase 2, preferring the project to be independently-led albeit with their active participation;

(c)	We have initiated discussions on how a pay and conditions framework can bring about “national consistency and local flexibility”;

(d)	We have agreed on SSSNB’s information requirements and written to DCSF to address identified information gaps; and

(e)	We have agreed a joint approach to communications and the requirements for a strategy and a detailed plan.  Required resources are also under discussion.  We have issued joint communications on our progress and have set up the SSSNB page on the OME website.

FACTORS IN THE REFERRAL LETTER TO HAVE REGARD TO

24.	Our considerations to date have been consistent with the 11 factors in the Referral Letter.  Our outputs, when further developed, will need to be tested against several of the factors covering the wider context including affordability, the inflation target, public sector pay policy, economic and labour market conditions (all factor c), recruitment and retention (f), 21st Century Schools (g), and the remodelling agenda and wider workforce (i).

25.	Specifically, the development of an implementation plan has included consideration of practicality (factor a) and administrative burdens and cost (b).  Our work on role profiles and job evaluation has sought to ensure equality and diversity (factor d), to incorporate developing skills and careers (h), and to include new entrant apprenticeships (k).  The SSSNB Executive Group has initiated discussions on national consistency and local flexibility (factor e) supported by papers from Employers and Unions.  All the strands of our work have drawn extensively on DCSF’s earlier commissioned research (factor j) as starting and reference points for negotiations.

C.	SSSNB REMIT

26.	We have sought clarification of our remit.  At previous SSWG meetings earlier in 2009 and at our first Full SSSNB meeting in July 2009, the Employers and Unions believed that the remit was wide-ranging and should cover all support staff terms and conditions in order to aid national consistency and to avoid equal value claims.  DCSF’s view was that the statutory remit specifically mirrored arrangements for school teachers but it did not automatically exclude those matters covered under the “Burgundy Book” for school teachers.  DCSF added that if an issue was raised outside the statutory remit it would be for Trade Unions and Employers to decide how it would be negotiated.  DCSF agreed to assist the SSSNB by indicating whether certain matters identified would/could be considered to be within remit.

27.	At our first Executive Group in July 2009, DCSF, Employers and Unions agreed that SSSNB’s approach should not be too prescriptive and therefore areas for negotiation would need to be worked through and tested as they arose.

28.	Part of our work has been to produce a core contract of employment which has necessarily covered all required contractual terms and led to the clear need to establish a School Support Staff Terms and Conditions Handbook.

29.	Once a draft Core Contract was ready for informal consultation in November 2009 DCSF informed us on its continuing work on the statutory remit and provided its definitions of remuneration, duties and working time.  It added that matters outside these definitions would require separate negotiations between Employers and Unions and could not be included in SSSNB agreements.  The majority of terms and conditions included in the draft Terms and Conditions Handbook, it said, appeared to be outside the remit of SSSNB.  DCSF advised us that the remit was restricted to three areas – remuneration, duties and working time – which correspond to just three items included in the draft Core Contract: job title, remuneration and working hours.

30.	Employers and Unions feel very strongly that all terms and conditions should be within the remit and we are awaiting further DCSF comments on the draft core contract.  If the remit excludes the majority of terms and conditions, it raises the question of which body should consider matters defined by DCSF as outside the remit.  The Unions believe that they had received assurances from Ministers and DCSF on a wide-ranging remit.  Employers have stressed that they believe the absence of a separate and statutory source for all terms and conditions would create a significant risk of triggering equal value claims.  Local Authorities have made clear that they are not prepared to risk re-opening single status agreements under the SSSNB remit as described by DCSF.  The Employers and Unions will be making joint representations to Ministers (provisionally scheduled for 10 December).

31.	The position is unsatisfactory as clarity on the remit is essential to the body’s progress.  It would be disappointing to lose the momentum gained in recent months if significant elements of the work are now designated as outside the remit.  If the remit is narrowed it would leave substantial issues of terms and conditions of employment for separate negotiations.  This seems to defeat the object of the SSSNB and makes the movement of school support staff away from the local government arena towards its own separate Body increasingly difficult.

PHILIP ASHMORE

SSSNB INDEPENDENT CHAIR

1 December 2009

# Footnotes

A National Pay and Conditions Framework for School Support Staff – BCHR, March 2009.

Deployment and Impact of School Staff – Institute of Education, University of London.

These standards are to facilitate the consistent collection of workforce data including from the Schools Workforce Census from 2010.

Equal Opportunities Commission’s equal pay review model.