Multidimensional Treatment Foster Care in England (MTFCE)

Annual Project Report

2008

National Implementation Team

|  | Contents | Page no. |
| --- | --- | --- |
|  | Executive Summary | 1 |
| 1 | The Role of the National Implementation Team | 5 |
| 2 | MTFC – Adolescent Programme (MTFC-A) Teams working towards MTFC Certification Round Four MTFC-A Teams | 6 7 7 |
| 3 | MTFC – Prevention Programme (MTFC-P) | 7 |
| 4 | MTFC – Children Programme (MTFC-C) | 8 |
| 5 | Project Plan and Timetable MTFC team development and support MTFCE programme development | 8 8 9 |
| 6 | MTFCE Training Programmes Induction day Progress, networking and update days The MTFC model Foster carer training | 12 12 13 13 14 |
| 7 | Independent Evaluation | 15 |
| 8 | MTFCE Audit Data Demographics of the entire MTFC-A sample MTFC-A as a placement for young people with complex needs Outcomes for young people leaving MTFCE Improving MTFC-A outcomes | 16 16 18 24 29 |
| 9 | The cost of MTFC-A 9.1 Calculating the costs of MTFC – Loughborough Cost Calculator Project 9.2 Comparative costs of MTFC | 32 32 33 |
| 10 | Foster Carers in MTFCE Foster Carer Audit Foster Carer’s views of MTFC Interview | 35 35 35 |
| 11 | Consultation with Oregon Social Learning Center | 37 |
| 12 | Network Partnership | 37 |
| 13 | Intensive fostering | 37 |
| 14 | The Learning So Far Learning from the treatment model Learning from the implementation process | 37 37 38 |
| 15 | Current Challenges Planning for long-term placements post MTFC Recruitment and retention of foster carers Independent evaluation | 39 39 39 40 |
| 16 | Aims For The Next Year Audit data Programme fidelity Training and support | 40 40 40 40 |
|  | Appendix 1: MTFCE Project staffing Appendix 2: MTFC-A Points and Levels System Appendix 3: MTFC-A Programme example Appendix 4: NSW Department of Health – MH-OAT Project CGAS Information Sheet | 41 42 44 45 |

Executive Summary

The Multidimensional Treatment Foster Care in England (MTFCE) programme, piloted by the Department for Children, Schools and Families (DCSF), for children with challenging behaviour and complex needs is now in its 5th year and has continued to progress well.  An exciting initiative this year has been the allocation of further government pump-priming money to set up eight new programmes to develop Multidimensional Treatment Foster Care services for 7 to 11 year olds (MTFC-Children) which aims to promote permanency either by returning children home to their families or to adoption or long-term foster care.  This builds on the growing success of the programme for adolescents and young children and has provided local authorities with the opportunity to meet the needs of the middle childhood age group.

There are thirteen MTFC-A (adolescents) teams; three under contract with the DCSF and ten in the Network Partnership contract. Four teams left the programme last year. One of these continues to provide a treatment foster care service with a full team using a different theoretical model, the other three are providing an intensive fostering service, and hence all four local authorities have increased their range of fostering provision. Thirteen teams currently have children in MTFC-A foster care placements and one team has children in MTFC-P (prevention) placements for 3 to 6 year olds. The further five MTFC-P teams are developing their infrastructure, recruiting staff and foster carers and will be making first placements in September 2008.  At 1st June 2008 a total of 150 young people, 80 boys and 70 girls, had been admitted to the programme since the first child was placed in April 2004. To date 100 children and young people have left the programme, 56 of these have successfully completed the programme (graduated) and moved to family or foster family placements or independent living.  33 have moved out of MTFC before 3 months (early leavers) and 11 have left later and moved to non-family based placements, such as residential children’s home (late leavers). 68% (38) of the graduates moved to long term foster placements, 20% (11) went home to family, 7% (4) moved to semi-supported lodgings to prepare for independence and 5% (3) went to ‘other’ placements; mother and baby unit, bed and breakfast, specialist therapeutic community.

The National Team and Evaluation Team

The MTFCE programme sites are managed and supported by the National Implementation Team based at the Maudsley Hospital in London, and Booth Hall Children’s Hospital in Manchester, in collaboration with the programme originators; TFC Consultants at the Oregon Social Learning Center (OSLC). This team is an innovative development by the DCSF commissioners intended to ensure coherence of approach and fidelity to the model which has been shown to increase positive outcomes. The programme for adolescents is in the process of being fully evaluated in a controlled study with a one year follow up by independent evaluators from the Universities of Manchester and York; however results from this research are not likely to be available until late in 2010. In order to provide preliminary information audit data have been collected on the MTFC-A programme by the National Team and will be collected similarly for the MTFC-P and MTFC-C programmes.

Characteristics of MTFC-A Young People

All of the children and young people admitted had high levels of complex needs. They were aged 10-16 years and two thirds of them had had three or more placements, all of which had disrupted or were not meeting their needs due to their very difficult behaviour.  Over 80% had a history of violence towards others, almost 50% had a history of offending, over half exhibited difficulties with sexual behaviour and were considered a risk to themselves or others, over one fifth had a history of fire setting. Two thirds had a history of absconding from previous placements. The majority had a history of neglect, physical, emotional or sexual abuse. Girls were significantly more likely to have a history of sexual abuse than boys, and boys were significantly more likely to have a history of physical abuse than girls.  They had much higher rates of psychiatric disorder compared to the whole care population (98.5% v 45%) and ten times higher than the general population (98.5% v 10%), higher difficulties scores on the Strengths and Difficulties Questionnaire (SDQ) and lower levels of global functioning as measured by the Children’s Global Assessment Scale (CGAS).

Outcomes for graduates

The National Team audit has also collated data on a group of 56 graduates who had successfully completed the programme after an average of 10 months in MTFC-A foster care placements at the end of March 2008. The graduates showed positive outcomes in most of the assessed areas of risk compared with the year prior to admission; 44.5% of the group of graduates entered the programme with convictions for criminal offences, only 13% had received a further caution or conviction on leaving, violent behaviour towards other people reduced from 75% on admission to 46% on leaving, of 30.5% young people with a history of self-harming behaviour on entry to MTFC-A only 4% had engaged in this behaviour.  Concerns about young people’s sexual behaviour risks to themselves and /or to others reduced during the time in the programme from 49% on entry to 28% on leaving. Absconding from placements reduced during the time in the programme from 59% on entry to 42.5% on leaving, incidents of fire setting decreased from 25% to 2%, alcohol use reduced from 34% to 29.5% during the placement period. Eight of the graduates were known to be using substances on admission to MTFC-A and ten at discharge. This needs further investigation; it may be that by increasing the supervision of young people more substance use is picked up.  Placements in mainstream and special schools increased from 75% to 84.5%. The numbers of graduates reported with behavioural difficulties in school fell from 78.5% on entry to 65.5% on discharge. Children and young people attending after school leisure activities increased by over one third during their placements. These results suggest significant reductions in difficulties in the expected direction and compare favourably with current data on poor outcomes for looked after children with complex needs.

Improving MTFCE Outcomes

Whilst the current data is encouraging, it also provides information about the differences between the graduate group and the early leavers group that could indicate areas to target for improved outcomes. The early leavers group showed higher levels of previous placement disruption and fewer school placements on admission. It may be useful to target such young people on admission and work to promote engagement and set up some structured educational provision (some teams work with their local Education for Children Looked After teams in this). Young people in the graduate group had much higher contact with the entire programme team than those in the early leaver group suggesting the importance of early engagement. Almost half of the early leaver group are reported to have chosen to leave the programme themselves (two of these young people were aged 11), it is worth further investigating the systems around these young people to ensure that a balance is struck between young people having appropriate choice and young people moving around, given the known detrimental effects of instability. This will be reported on in the next project report.

MTFC Foster Carers

To date the audit data collected by the MTFCE National Implementation Team has focused on the young people placed in the programme.  More recently, and in recognition of their central importance in the programme, we have begun to collect some audit data on the foster carers and to interview them about their views on MTFCE. Early audit data is presented in this report and we will report much more fully in the 2009 Project Report.

Building capacity and capability through sustainability

Twenty local authorities are currently using the MTFC model and have set up, or are setting up new foster placements. There are approximately 50 MTFC placements available to date with another 15 MTFC-P placements expected to commence in the autumn. All of the ten sites in the Network Partnership contract have now secured long-term funding. Two of the teams (Dudley and Solihull) have MTFC for all three age groups within their provision for looked after children. Two further teams have MTFC for two of the age groups (North Yorkshire and Oxfordshire). Two of the teams have additionally developed programmes designed to offer training and support to foster carers offering long-term placements to children graduating from MTFC or children with similar needs. The teams who have left the national programme continue to provide services that have increased their range of provision locally. Learning from the MTFC-A programme has influenced local authorities to consider the needs of children in residential establishments for assessments and clear behaviour management strategies and of the need for greater provision of support for mainstream fostering.

The recent publication of the government White Paper, Care Matters: Time for Change, emphasises the crucial role that evidence based programmes, such as Multidimensional Treatment Foster Care, play in improving the lives and long-term outcomes for children in care. The lessons learned from implementing the programme for adolescents has led to a number of innovations and developments which it is hoped will transform the landscape for children looked after in mainstream and specialist fostering and those on the edge of care.

Government reforms include support for local authorities to deliver better value for money and to use more evidence-based interventions.  Joint Area Reviews (JARs) will provide some incentives as inspectors will be asked to judge how services are contributing to improving outcomes for children in care.  The proposal that agencies take a longer-term view on local budgets and avoid making decisions based on short term funding pressures is much welcomed and may help to influence a longer-term approach to developing and sustaining these projects.

Network Partnership

The National Implementation Team have now formally signed an agreement with Treatment Foster Care associates at the OSLC, to become the UK Network Partner. This will enable us to provide implementation services, training and consultation in the MTFC programmes for new teams wishing to develop the model in the UK outside the DCSF funded programme and for existing MTFC-A teams who wish to contract for further services at the end of the current contract. This is an exciting and important step forward in sustaining and developing the programme over the longer term and developing a UK base for these evidence based programmes.

Contents of this report

This is the 4th annual project report published by the National Implementation Team.  For the MTFC-P and MTFC-C sites, the theoretical background and information can be found in the 1st and 2nd year reports. The current report provides an update of project development and activity across the national sites, outlines the progress and developmental plan for the teams, the development of the training programmes for the clinical staff and foster carers and the successes, challenges and learning so far.  The ongoing audit data and analysis of the young people admitted to the scheme makes up a substantial part of this year’s report.

Rosemarie Roberts						Dawn Walker

Project Director						Project Manager

National Implementation Team				National Implementation Team

1.	The Role of the National Implementation Team

Evidence from a number of trials concludes that treatment fidelity is a major determinant of outcome and that a high level of fidelity and model adherence is associated with positive outcomes. The National Team was commissioned by the Department for Education and Skills (DfES) now DCSF in 2003 to provide this consistency of training and fidelity to the model in order to ensure the best possible outcomes for the children, young people and their families in this innovative national project.

The National Team’s staffing this year includes four staff (2.8 full time equivalent) in Manchester plus a part-time administrator, six staff members (3.2 fte) in London plus a project administrator, and one part time and one full time assistant psychologist based in Manchester and London respectively to manage the audit data.

The Project Executive Director, Professor Stephen Scott, Reader in Child Health at the Institute of Psychiatry, Kings College, and Child and Adolescent Psychiatrist at the Maudsley Hospital, London, is a leader in the field of conduct disorder and parenting in the UK and has many publications of clinical trials in this area. As the Kings lead representative, Professor Scott was awarded, along with consortia partners Parenting UK and the Family and Parenting Institute, the highly prestigious £30 million pound government contract to develop the National Academy for Parenting Practitioners to support evidence-based approaches to parenting across the country.

The rest of the National Team at the Maudsley and Booth Hall Children’s Hospital in Manchester are systemic family therapists and clinical psychologists with a high level of expertise in health, social care, education and offender services, training, consultation and research, and bring a great deal of knowledge, experience and expertise to the programme. The original task of training and ensuring treatment fidelity has developed into a comprehensive consultancy role incorporating management consultancy from the development stage, specific training in the three MTFC models (both alongside staff at the OSLC and independently), a programme of additional training for clinical staff, plus consultation for teams pursuing applications to become certified with OSLC as MTFC teams. The National Team became Network Partners with the MTFC programme originators at OSLC in 2008. This enables them to offer the full range of MTFC consultation services to organisations outside of the pilot project wishing to set up MTFC-A teams in the UK.

Figure 1. Model of consultation to current MTFC-A, MTFC- P and MTFC-C sites

The National Team provides development support on implementation, training, clinical consultation and support in the treatment model to the clinical teams, support for local and national evaluation and audit, and monitoring and guidance with regard to model adherence. This innovative method of project management includes formal reviews and feedback to the project teams, live and video supervision and written feedback to ensure the teams are given optimum support in taking the programme forward.

###### 2.	MTFC-Adolescent Programme (MTFC-A)

Over the past 4 years the DCSF has awarded start-up funding to 20 local authorities with their education and health partners to develop MTFC programmes in a series of competitively tendered bids. Two sites decided to withdraw in the very early stages and repay the grants due to difficulties including staff and foster carer recruitment and concerns about sustainability. The team in the Wirral left the MTFC project in 2006 because they developed their service using a different model from the MTFC model.

In April 2006, at the request of our consultants in Oregon the teams in rounds 1-3 were asked to consider whether or not they wished to work towards certification as an accredited MTFC site. This meant they would be able to continue to use the MTFC name and website facilities and would need to demonstrate their ability and willingness to adhere to the treatment model and continue or re-engage in regular consultation with the National Team.  Ten of the teams chose to do so. The three that did not (Cheshire, South Gloucestershire and Northumberland and North Tyneside) continued to provide an intensive fostering service using a different model of service from the MTFC model. The DCSF contract period with the teams from rounds 1-3 ended in March 2008.

All of the 4th round sites have young people in placement. There are currently 44 children and young people in MTFC foster care placements in 13 sites across England at the time of writing (June 2008).

2.1	Teams working towards MTFC Certification

The 10 teams working towards MTFC Certification are in Dorset, Dudley, Gateshead, Hammersmith and Fulham, Kent, North Yorkshire, Reading, Solihull, Southampton and Wandsworth. All 10 teams are no longer in contract with the DCSF. They have secured either long-term or mainstream funding and are embedded within fostering provision locally. Between them they are providing foster placements for 41 young people with complex needs.

All the teams received their training in the MTFC model between 2003 and 2006 and are now training new carers themselves, thus building local expertise.

For the process of certification teams need to collect data on different criteria laid down by OSLC. These are: the outcomes of young people at the time of moving on, therapy components, behavioural components, staffing and training. In addition they have to select recordings of three clinical meetings and three foster carer meetings which demonstrate their fidelity to the MTFC model and send them to be reviewed with their application.

2.2	Round Four MTFC-A Teams

The fourth round selection was confirmed in the autumn of 2005 and an induction day facilitated by the DCSF and the National Team for the 4 new teams was held in December 2005. Unfortunately, during 2006, one of the sites suffered considerable financial changes in combination with a change in demographics of the looked after children population and severe understaffing in the fostering services which culminated in the decision to withdraw from the programme at the early development stage and repay the grant funding to the DCSF.

The 3 remaining teams were trained by the National Team alongside staff from OSLC in September 2007 with the foster carer training following in October 2007. A second round of foster carer training has taken place with staff from the teams working alongside the National Team to gain expertise in MTFC training. All three teams have placements and are receiving positive feedback about their work from OSLC.

The round 4 teams are fully committed to the evaluation of the MTFCE pilot and have included all of their young people in the randomised controlled trial.

3.	MTFC-Prevention Programme (MTFC-P)

This programme is for young children aged 3-6 years. Six local authorities were awarded pump-priming funding in 2006.  Three of the teams awarded funding for this programme are also running the MTFC programme for adolescents, three are new to MTFC programmes but are benefiting from the existing knowledge of the experienced teams and senior managers.

It was anticipated that placements would be made in the spring of 2008. However, recruiting to the Programme Supervisor (Clinical Lead) posts proved to be difficult for three out of the six teams. They have all now recruited to this post and all the Programme Supervisors have been trained in the MTFC-P model in Oregon.

National training for MTFC-P clinical teams and foster carers was held in February 2008, facilitated by staff from OSLC. Further training for clinical teams and foster carers will take place in September 2008. In order to facilitate placements for teams that were closer to the original schedule the National Team has provided training in the North and South of England to enable teams to make placements. One team made a first placement in May 2008 and two teams are due to make placements in July 2008.

4.	MTFC-Children Programme (MTFC-C)

This year saw the introduction of a further exciting opportunity for local authorities and partner agencies to tender for pump-priming funding to develop the MTFC-C programme for 7 to 11 year olds. Eight local authorities were granted funding in May 2008 and attended an induction day organised by the DCSF and the National Team on 3rd June. One of the local authorities has an MTFC-P team (Oxfordshire). Two of the local authorities, Dudley and Solihull, have shown commitment to the MTFC model such that they have MTFC for all three age groups. Senior managers in Solihull have credited MTFC with a reduction in the numbers of their children in residential placements.

The MTFC-C sites are currently in the developmental stage of setting up systems and protocols, and advertising for staff. It is anticipated that teams and foster carers will be trained in the spring of 2009 with placements commencing by May 2009.

5.	Project Plan and Timetable

5.1	MTFC Team Development and Support

The MTFC-A and MTFC-P local sites are supported by the National Team to develop in three main phases following their successful application for start-up funding. The new MTFC–C teams will be similarly supported.

Developmental stage

During the developmental stage (see Figure 2) the role of the multi-agency teams is to set up steering groups; develop forward financial plans and work on sustainability issues; recruit clinical staff and foster carers, develop literature and information leaflets for foster carers, children, families and referrers and develop protocols and referral criteria for the programme.  This stage takes a minimum of eight months and for some teams much longer, due to the need to negotiate the continuing financing of the posts, and long-term commitment of all agency partners. A named site consultant from the National Team is appointed to each site and will visit the site every three to four weeks, meet with staff as they are appointed into post, attend the steering group meetings and offer additional telephone or email consultation. The site consultant aims to provide developmental advice on setting up a model adherent MTFC programme to steering groups and senior managers. Sample job descriptions for the clinical staff, leaflets and consent forms are provided. Consultants may also be available to make presentations to partner agencies, steering groups and PCT’s (alongside programme sites) and sit on interview panels as appropriate.

The full clinical team needs to be in place and staff and foster carers must complete the specialist MTFC training prior to placing the first child in a MTFC foster care placement.  The National Team also provides consultation days or progress update days to enable the sites to meet other programmes at the same stage, and share ideas, problems and solutions.

Intensive Support

Once the clinical team is in place and meeting on a regular basis the site consultant will attend each clinical and foster carer meeting (which are also videoed) and meet with the Programme Supervisor individually, for approximately 3 months, providing weekly direct clinical consultation and support in the treatment model to the clinical teams (see Figure 3). A sample of video recordings (including children’s group recordings for MTFC-P) will be sent to the TFC programme developers at OSLC for consultation purposes and to ensure model adherence and fidelity. Recruitment of foster carers continues on a rolling programme.  At the end of 3 months the site consultant will conduct a formal review to provide feedback to the team regarding their progress, current strengths, and areas to target for improvement. A rolling programme of ongoing training is also provided to support clinical team staff and train new foster carers following the local team’s assessment and approval process.

Consolidation

After the formal review the site consultant, Programme Supervisor and Programme Manager agree a step-down process during which the site consultant will reduce the number of site visits to two weekly then monthly, then three monthly. Consultation will then be via a regular weekly telephone call to the Programme Supervisor, written feedback notes, video review of the clinical and foster carer meetings plus email and telephone correspondence as appropriate. A site visit will be arranged approximately every three months to the clinical team and foster carer meetings to review the team’s progress and provide face to face consultation and feedback on programme progress. A sample of video recordings will be sent to OSLC for consultation and feedback to the National Team on this consultation process.

Sites under the DCSF grant conditions continue to have access to national training, training for Programme Supervisors and Foster Care Recruiter/Supporters in training the foster carers independently and networking days as required. Sites under the Network Partnership have separate arrangements for training as per their contracts.

5.2	MTFCE Programme Development

There are seventeen teams under contract with the DCSF; three MTFC-A teams, six MTFC-P teams and eight MTFC-C teams. These teams are in receipt of services to promote their development, intensive support or consolidation. There are a further ten teams using the MTFC-A model who are contracted with the National Implementation Team under the Network Partnership agreement with OSLC. These teams are working towards MTFC Certification.

Figure 3 shows the current stage of development of the project sites and the involvement of the National Team site consultant from April 2008 projected until the end of March 2010.

Figure 2.  Project Team Development and Time Line for  all MTFCE Programmes

## CLINICAL

## TEAM

STEERING

GROUP

FOSTER

CARERS

## Month	1	2	3	4	5	6	7		8

6.	MTFCE Training Programmes

In addition to supporting the development and implementation of the model in the sites, the National Team has been commissioned to provide training in the MTFC model to ensure consistency of approach and fidelity to the treatment programme. In order to achieve this, core training in the MTFC model has been provided for each round of the MTFC-A programme and for the MTFC-P programme for clinical staff and foster carers prior to young people and children being placed. OSLC staff have regularly been invited to London to train clinical staff and foster carers in conjunction with the National MTFCE Team. In addition the National Team has provided training in the assessment requirements for the English programme.

The National Team aims to provide the following training programme for all new sites awarded start up funding;

6.1	Induction Day

This provides an overview of the MTFC model, the research evidence from randomised control trials in the USA, the English programme content, the role of the National Team and DCSF expectations of the sites.

Figure 4. Numbers Attending MTFC-A , MTFC-P and MTFC-C Induction Day

MTFC-A

MTFC-P

| MTFC-P 4-Dec-06 | Dudley | 4 |
| --- | --- | --- |
|  | Manchester | 3 |
|  | North Yorkshire | 2 |
|  | Oxfordshire | 6 |
|  | Solihull | 5 |
|  | West Sussex | 5 |

MTFC-C

| MTFC-C 3 Jun 08 | Barking and Dagenham | 5 |
| --- | --- | --- |
|  | Blackburn with Darwen | 3 |
|  | Cambridgeshire | 4 |
|  | Cumbria | 5 |
|  | Oxfordshire | 3 |
|  | Hackney | 3 |
|  | Solihull | 2 |
|  | Dudley | 0 |
|  | Total to date | 144 |

6.2	Progress, Networking and Update Days

Progress and Update Days provide an opportunity for the lead managers to meet with colleagues from other developing sites to network, exchange information concerning common dilemmas and possible solutions and to gain further information about the model e.g. ideas about successful recruitment of foster carers. In the last year the developing MTFC-P sites met for update and networking days in London in September 2007, December 2007 and June 2008. These days were used to update the DCSF on developmental progress, potential challenges (such as use of respite placements) and to share ideas and successes (such as joint posts with Children’s Centres). An update day for the developing MTFC-C teams has been arranged for late September 2008.

In addition a rolling programme of training/consultation and networking days has been provided by the National Team. Smaller training/consultations have been held to allow individual clinical team members to network, learn from each other and provide ongoing support for their specific roles within the clinical teams. For example the training for skills workers included skills practice and role plays and the foster carer recruiter day included sharing ideas for recruitment and for moving children and young people on to permanent placements.

In the last year 8 Networking Days have been held for: Birth Family Therapists in February 2008, Education Workers in November 2007 and March 2008, Skills Trainers in March 2007, Individual Therapists in May 2008, Programme Supervisors in September 2007 and January 2008 and Programme Managers with Foster Carer Recruiters in January 2008.

6.3	The MTFC Model

Specific training in the core principles, history, philosophy and practice tools of the MTFC model takes place with the whole clinical team. The training provides the teams with the basic skills and knowledge needed to set up and run the treatment programme for children and young people. The role of each member of the team is differentiated and clearly set out and the operational aspects of the programme outlined. Staff from TFC Consultants have joined the National Team to facilitate each of the initial national trainings for each of the programmes. Subsequent training in both MTFC-A and MTFC-P for new staff joining teams has continued to run on a rolling programme.  Clinical team staff from earlier rounds have also contributed to the training programmes to share their experiences.

This year two MTFC-A Clinical Team training courses have been held in Manchester in September 2007 and London in February 2008. Two MTFC-P training courses have been held for Programme Supervisors. These have taken place at the Oregon Social Learning Center, USA in November 2007 and June 2008. A training course for MTFC-P Clinical Teams took place in London in February 2008 with a further course planned for September 2008.

Figure 5. Total numbers of clinical team staff trained in MTFC models since 2003

| Round 1 | Dorset |  | 30 |
| --- | --- | --- | --- |
|  | Durham |  | 24 |
|  | Solihull |  | 30 |
|  | Wandsworth |  | 34 |
|  | Wirral |  | 12 |
| Round 2 | Cheshire |  | 10 |
|  | Dudley |  | 25 |
|  | Kent |  | 15 |
|  | Southampton |  | 16 |
| Round 3 | Gateshead |  | 10 |
|  | Hammersmith & Fulham |  | 14 |
|  | Northumberland & N. Tyneside |  | 8 |
|  | North Yorkshire |  | 6 |
|  | Reading |  | 8 |
|  | South Gloucestershire |  | 21 |
| Round 4 | Salford |  | 13 |
|  | Tower Hamlets |  | 11 |
|  | Trafford |  | 11 |
| MTFC-P | North Yorks |  | 2 |
|  | Manchester |  | 4 |
|  | West Sussex |  | 4 |
|  | Solihull |  | 5 |
|  | Dudley |  | 3 |
|  | Oxfordshire |  | 7 |
|  | Total to date |  | 323 |

6.4	Foster Carer Training

Foster carer training takes place once the carers have completed the “Skills to Foster” training provided by the local authority, have been formally assessed and then approved by panel. They then receive the additional training in the relevant MTFC model. This provides the basic information needed to understand the principles and practice of operating the programme in the foster carers’ home.

Since last year foster carers from the English project have also contributed to the training and their videos were thoroughly enjoyed by the prospective new carers. The two day training course includes a number of case examples, practice exercises and role plays, information about how attachment theory relates to the behavioural programme and examples of dealing with specific behavioural problems in the English legal and cultural context.

Figure 6. Total numbers of Foster Carers trained in MTFC

| Round 1 | Dorset |  |  | 31 |
| --- | --- | --- | --- | --- |
|  | Durham |  |  | 20 |
|  | Solihull |  |  | 12 |
|  | Wandsworth |  |  | 24 |
|  | Wirral |  |  | 12 |
| Round 2 | Cheshire |  |  | 8 |
|  | Dudley |  |  | 29 |
|  | Kent |  |  | 28 |
|  | Southampton |  |  | 16 |
| Round 3 | Gateshead |  |  | 13 |
|  | Hammersmith & Fulham |  |  | 8 |
|  | Northumberland & N. Tyneside |  |  | 9 |
|  | Reading |  |  | 5 |
|  | North Yorkshire |  |  | 17 |
|  | South Gloucestershire |  |  | 10 |

| Round 4 | Salford |  | 6 |
| --- | --- | --- | --- |
|  | Tower Hamlets |  | 5 |
|  | Trafford |  | 11 |
| MTFC-P | Oxfordshire |  | 4 |
|  | Total to date |  |  | 268 |

The recruitment of foster carers is a continual process and is not consistent across the sites. As a result the National Team have made foster carer training available on a rolling programme in order to train carers at reasonable time intervals following their assessments and approval as foster carers. The aim is to train Programme Supervisors and Foster Carer Recruiters to be able to train their own carers and a number of teams are now proficient in the materials and able to deliver their own courses. All the teams from round 4 will be expected to be able deliver their own training by March 2009. Figure 6 above shows that a total of 268 carers have been trained since the programme began. Included in these figures are: some carers who received separate “top-up” training at their request, plus partners and supporters for example adult children living at home who wished to understand and help with the programme. In the last year two MTFC-A Foster Carer Training courses have been held in Manchester in September 2007 and July 2008.

The next foster carer training courses are scheduled to take place for the MTFC-P teams in September 2008 with the OSLC programme developers.

7.	Independent Evaluation

The independent national evaluation team from the universities of Manchester and York was appointed by the DCSF in the autumn of 2004 and has worked closely with the National Team in understanding the structures and systems of the programme sites and determining the practicalities of undertaking a randomised control trial (RCT) alongside a case control study. The Care Placements Evaluation (CaPE) team has worked hard on recruitment of young people into the study as more teams have joined the national programme. The data collection time period has been extended in an attempt to manage some recruitment delays and it is hoped that as the later rounds increase their numbers of placements this will increase the numbers of children available to the RCT.

8.	MTFCE Audit data

All MTFCE teams have been asked to collect audit data on children and young people placed in the programme to be collated and analysed by the National Team. The data provides the national programme and individual teams with general information regarding the status of children entering and leaving MTFCE including demographic data, difficulties experienced by children and young people, educational attainment and criminal offences. There is also audit data on outcomes including changes in objective measures, indications of the factors contributing to successful placements and treatment outcomes. All three MTFCE programmes will be collecting data once children are placed. For the current project report the data comes from the MTFC-A teams as there is just one placement in the MTFC-P programme and the MTFC-C programmes are yet to place.

  - Demographics of the entire MTFC-A sample

A total of 150 young people had been admitted to the MTFC-A programme from the first placement in April 2004 up to the point of collating and analysing the current audit data at the end of March 2008. General demographic data is collected on all young people placed in MTFC-A.

8.1.1	Age and Gender

Figure 7. Age and Gender of Young People on Admission to MTFC-A

Of the 150 children and young people admitted to the MTFC programme between April 2004 and March 2008, 53% (80) were boys and 47% (70) were girls. The last year of operation has seen 26 boys and 23 girls admitted to the programme. The mean age for all children was 12.57 years, for the boys it was 12.04 years and for the girls slightly older at 13.19 years. The mode for boys is 12 years and the mode for girls is both 14 and 15 years.

Although the programme is designed for older children, eleven children under ten years have been admitted to MTFC-A placements.  One team (Solihull) requested to work with younger children from early in their development due to their referrals coming largely from the 7-11 age group. This was agreed and they adapted the adolescent model for this younger age group. Six of the eleven children under ten years are from the Solihull site.

For other teams, the most common reasons for admitting a younger child into MTFC-A were acute concerns about their presenting behavioural difficulties and lack of alternative specialist placements. Teams working with younger children have made some adaptations to the adolescent model to ensure developmentally appropriate interventions are being used.

8.1.2	Ethnicity

The majority of children who came into the programme were White British (86.5%). 6% are of Mixed heritage, 2% are Black and 5.5% Other.

8.1.3	Legal Status at admission

Half of young people (48%) admitted to MTFCE were accommodated by the local authority, just under half (45%) had full Care Orders and 7% were on Interim Care Orders. Slightly higher numbers of boys were on full Care Orders than girls.

8.1.4	Last placement prior to MTFC-A

Figure 8. Last Placement Prior to MTFC-A (n=138)

Figure 8 above shows that 34% (47) of young people were admitted to MTFC-A directly from residential care and were an equal mix of boys and girls. 44% (61) came from foster care (either local authority or independent provision) with slightly more girls in this group. The remainder were from a mixture of birth or extended family (14%), secure provision (either Young Offender Institution or Secure Unit (6.5%) and one case (1.5%) from hospital.  The gender split shows that more than twice as many boys were admitted from their family or friend network and girls were more likely to be admitted from secure settings.

8.1.5	School placement on entry to MTFC-A

Table 1. School Placement on entry to MTFC-A (n=139)

|  | Boys | Girls | Total |
| --- | --- | --- | --- |
| Mainstream | 24 (31%) | 29 (47%) | 53 (38%) |
| Special school | 22 (28.5%) | 16 (26%) | 38 (27.5%) |
| Education other than school | 13 (17%) | 5 (8%) | 18 (13%) |
| Without a school place | 18 (23.5%) | 12 (19%) | 30 (21.5%) |
| Total | 77 (100%) | 62 (100%) | 139 (100%) |

Of the 139 young people for whom we have data, 65.5% (91) had a school place on admission to MTFC-A either within mainstream or special school.  73% (45) of the girls had a school place compared with 59.5% (46) of the boys. 34.5% (48) had no mainstream or special school places, and most were provided with education in a special unit such as a Pupil Referral Unit (PRU). 60% of young people were in full time educational provision on entry to MTFC-A, 31% had part time educational provision and 9% had no educational provision.

8.1.6	Wechsler Intelligence Scale for Children (WISC) or WASI

Table 2. IQ scores on entry to MTFC-A (n= 67)

|  | IQ at T1 |
| --- | --- |
|  | <70 | 71-80 | 81-100 | >101 |
| No. of Young People | 15% (10) | 22% (15) | 42% (28) | 21% (14) |

All young people referred to the MTFC-A programme receive a full assessment, part of which is psychometric testing. Table 2 above shows that of the 67 young people for whom there is valid data, about a fifth have scores in the 71-80 borderline learning disability range and 15% (10 young people) have scores below 70 (in the general learning disability range). Some of these young people were in mainstream school with no additional resources and it was only after the MTFC-A assessment that they were able to access educational support. The MTFC-A programme has not been designed for young people who are identified as having learning disabilities because of the level of cognitive ability required to make use of the treatment model. Some teams found that these young people needed more support and more simplified individual programmes than young people with higher cognitive ability. This information was useful in planning for their future placements. Just under half of the young people have IQ scores in the 81-100 low average range, and another fifth score above 101, in the average, high average and superior ranges. The mean score was 87.10 and the range 58-127.

  - MTFC-A as a placement for young people with complex needs

The MTFCE programme is designed for young people with complex needs and who have experienced placement disruption. It is therefore important to ensure that the programme is being utilised by this small group of young people with a high level of need. The MTFCE audit collects data on mental health needs, family history and significant harm, high risk behaviours, placement moves and educational needs.

    - Mental Health Needs

These are being assessed using a number of established measures and data is collected about medication used in Child and Adolescent Mental Health Services (CAMHS).

- Development And Well Being Assessment (DAWBA)

The DAWBA was developed by Professor Robert Goodman and has been used in a study funded by the Department of Health comparing the mental health of a group of 1500 Looked After Children with a sample of children living in private households. Using this measure enables the MTFC-A group of young people to be compared with the two samples in the ONS survey.

Table 3. Mental health of MTFC-A Young People Compared with ONS Surveys

| ICD Disorder (definite) | MTFC-A cases 2008 n=66 | ONS Survey of looked after children | ONS general population sample |
| --- | --- | --- | --- |
| Any psychiatric disorder | 98.5% | 44.8% | 9.6% |
| Multiple psychiatric diagnoses | 75.75% | 13.0% | 2.2% |
| Any emotional disorder | 42.42% | 11.7% | 3.7% |
| Separation anxiety | 9% | 0.4% | 0.4% |
| Social phobia | 1.5% | 0.7% | 0.3% |
| PTSD | 12% | 2.1% | 0.2% |
| Generalised Anxiety | 19.7% | 2.1% | 0.8% |
| Other Anxiety | 7.5% | 3.9% | 0.9% |
| Depression | 4.5% | 4.3% | 0.9% |
| Any Conduct Disorder | 87.9% | 38.9% | 5.8% |
| ODD | 22.4% | 11.4% | 3.0% |
| Socialised CD | 3.4% | 14.3% | 1.3% |
| Unsocialised CD | 10.3% | 5.6% | 0.8% |
| Other CD | 1.7% | 5.4% | 0.6% |
| Hyperkinesis | 18% | 7.3% | 1.5% |
| Less common Disorders (tic, eating, autistic) | 4.5% | 3.7% | 1.3% |

As can be seen from table 3 above, young people coming into MTFC-A placements are twice as likely to meet the criteria for any psychiatric disorder as the children looked after surveyed in 2003. They are almost six times more likely to meet the criteria for multiple psychiatric diagnoses. The number of young people meeting the criteria for conduct disorder is double that of the young people looked after in the ONS survey, which is to be expected since the MTFC-A programme was developed to meet the needs of this group of young people. However, young people coming into the programme show almost four times the level of emotional disorder when compared with the ONS sample of looked after children. Over one third of young people in the MTFC-A sample met the criteria for both conduct disorder and emotional disorder with 6% meeting the criteria for conduct disorder, emotional disorder and hyperkinesis. These findings are reflected in the individual programmes for young people, many of which contain anxiety management alongside interventions for behavioural change.

- Strengths and Difficulties Questionnaire (SDQ)

This assessment measure has been adopted for the screening of looked after children for mental health needs from April 2008. It is also part of the Child and Adolescent Mental Health Service Outcome and Research Consortium (CAMHS CORC) data set. It includes questionnaires for young people themselves (if aged 11 or older), their carers and teachers.

Table 4.  Strengths and Difficulties Questionnaires (SDQ)

|  | Parent / Carer Total Difficulties Score at T1 (n=89) | Teacher Total Difficulties Score at T1 (n=73) | Young Person Total Difficulties Score at T1 (n=89) |
| --- | --- | --- | --- |
| 0 – 11 average | 3% | 16.5% | 18% |
| 12 – 15 borderline | 8% | 12.5% | 18% |
| 16 + high | 89% | 71% | 64% |

Of those for whom we have data, 89% of young people had difficulties in the high range on the SDQ Parent/Carer, 71% had difficulties in the high range according to teacher ratings and of the 89 young people who completed the self rated young persons SDQ, 64% had difficulties in the high range.

- Children’s Global Assessment Scale (CGAS)

The Children’s Global Assessment Scale (CGAS) is a measure developed by Schaffer and colleagues at the Department of Psychiatry, Columbia University to provide a global measure of level of functioning in children and adolescents. The measure provides a single global rating only, on scale of 0-100. In making their rating, the clinician makes use of the glossary details to determine the meaning of the points on the scale. A higher score indicates better functioning and a lower score indicates greater difficulties in functioning.  This measure is also used by the CAMHS CORC.

Table 5. CGAS Scores Whole Group on entry to MTFC-A

| CGAS | T1 n=96 |
| --- | --- |
| Mean score | 50.27 |
| Range | 25 - 75 |

Mean scores on entry to the MTFC-A programme for this group were 50.27 which is on the border between “60-51 Variable functioning with sporadic difficulties” and “50-41 Moderate degree of interference in functioning” The range is 25 to 75. (See C-GAS Appendix 4).

    - Medication

22 (16.5%) of the 134 young people for whom data were available were in receipt of medication for a variety of mental health difficulties including ADHD, depression, epilepsy, psychosis, and sleep problems at the time of admission to the programme. This is four times as many as in the 2003 ONS Survey (4%).

    - Family Context and History of Significant Harm

Information is collected about the family context of young people placed in MTFC-A. Family violence is known to impact on children and young people and maternal drug and alcohol use can affect children in utero. Parental mental and physical ill health and the death of a parent are stressful life events for children.

- Family Context

Table 6. Family Context

|  | Boys | Girls | Total |
| --- | --- | --- | --- |
| Family Violence (n=107) | 51 (81%) | 35 (80%) | 86 (80%) |
| Family Alcohol Misuse (n=104) | 25 (42%) | 23 (52%) | 48 (46%) |
| Family Substance Misuse (n=105) | 31 (52%) | 13 (30%) | 44 (42%) |
| Parental Mental Illness (n=105) | 40 (66%) | 30 (68%) | 70 (67%) |
| Parental Physical Health Difficulties (n=104) | 12 (20%) | 10 (22%) | 22 (21%) |
| Death of Parent (n=109) | 8 (13%) | 3 (7%) | 11 (10%) |

Most (80%) of the children and young people for who we have data had a family history of violence, 67% had a parent with mental illness, 46% had a parent who misused alcohol, and 42% who misused substances.  21% of young people had a family history of parental physical ill health and 10% had experienced the death of a parent.

# History of Significant Harm

# The association between trauma and physical and/or sexual abuse is well-documented. More recently, the effects of neglect on the child’s developing brain have been researched and described. These experiences leave young people vulnerable to developmental and emotional difficulties.

# Figure 9. History of Significant Harm on entry to MTFC-A (n=128)

Data was available for 128 young people. 93% (119) had experienced abuse or neglect. 65% (83) had experienced two or more types of abuse, 33% (42) had experienced three or more types of abuse and 8% (10) children had experienced all four categories of abuse. In the general children looked after population 62% become looked after as a result of abuse or neglect.

For the 74 boys, 96% (71) had a history of abuse and/or neglect and for the 54 girls 90% (49) had a history of abuse and/or neglect. Gender differences in the type of abuse experienced were that a higher percentage of girls had experienced sexually abuse and a higher percentage of boys had experienced physically abuse.

    - High risk behaviours on entering MTFC-A

It was anticipated that young people coming into MTFC-A placements would exhibit behaviours which are known to put their placements at risk of disruption. Information is collected about rates of offending, violence, self-harm, absconding, fire-setting and alcohol and drug use. The information on sexual behaviour difficulties covers young women engaged in health-risking sexual behaviour in addition to young people whose sexual behaviour poses a risk to others.

Figure 10. High risk behaviours of young people on entry

Of the young people admitted to MTFC-A on whom there is data, almost 50% (n=67) were involved in offending behaviour (five times higher than the 9.6% of looked after children cautioned or convicted in 2006).  25% (n=34) were using substances compared with 5% of looked after children having a substance misuse problem in 2006. 47% were using alcohol compared with the 25% found by Meltzer and colleagues in 2003. The audit data collected suggests that the MTFC-A teams are working with the target population in relation to high risk behaviours.

    - Numbers of placements prior to MTFCE

# One early aim of the MTFC-A pilot programme was to provide placements for young people who had experienced placement disruption and to enable these young people to experience stability. A third of young people admitted to MTFC-A (n=47) had had between none and two prior placements with 12 of them being admitted from home. The use of MTFC-A placements for young people admitted directly from home occurs where there is a clear need for specific work with the birth family. Placement panels have seen it as preferable for a young person to come into an MTFC-A placement where one team can work with the young person, the foster carers and the birth family. The other two thirds had had three or more placements with almost half of them having had four or more previous placements. Twenty-one young people (15%) had had more than ten placements and one young person had twenty-six placements.

Figure 11. Number of previous placements (n=131)

8.2.6	Educational needs on entry to MTFCE

- Special Educational Needs (n=136)

28% of all children in care have a statement of special educational needs (SEN), compared with 3% of all children. 48% (65) of young people entering MTFC-A had full statements of special educational needs, showing that the MTFC-A group have more educational needs than looked after children generally. 11% (15) were on school action plus, and 3% (4) were on school action. Rather surprisingly, 38% (52) had no identified special educational needs despite considerable reported difficulties in school.

- Educational Attendance (n=124)

75% (93) of young people were described as mostly attending their educational place and 22% (27) were frequently not attending. This is higher than the 13% missing 25 days of school found in the 2006 Outcome Indicators.

- Behavioural Difficulties in School (n=134)

82% (110) of young people had behavioural difficulties identified by teaching staff in their school or education context.

“I had some [problems] at school with anger management”

8.3	Outcomes for young people leaving MTFCE

100 young people have left the MTFCE programme between 2004 and the end of March 2008. 56 of these are classed as graduates using the criteria set by OSLC; they have both completed their individual programmes and moved to family based placements (mainstream foster care, extended family, or independent living). 33 young people are classed as early leavers and left the programme having completed less than 3 months. 11 young people are classed as late leavers and stayed in the programme for more than 3 months but either did not complete their individual programme or moved from MTFC to non-family based placements. The rationale for drawing the distinction at 3 months is that OSLC research has shown a smaller but still positive effect for those young people who stayed for 3 months or longer but who are not classed as graduates.

    - Mental health outcomes

- Strengths and Difficulties Questionnaire (SDQ)

Table 7.  SDQ Scores on entry and discharge for graduates

|  | Parent/Carer Total Difficulties Score (n=44) | Teacher Total Difficulties Score (n=29) | Young Person Total Difficulties Score (n=33) |
| --- | --- | --- | --- |
|  | T1 | T4 | T1 | T4 | T1 | T4 |
| 0 – 11 average | 0% | 4.5% | 21% | 14% | 12% | 30% |
| 12 – 15 borderline | 11.5% | 11.5% | 17% | 27.5% | 9% | 21% |
| 16+ high | 88.5% | 84% | 62% | 58.5% | 79% | 49% |

Of the cases for whom we have data, 88.5% of young people had difficulties in the high range on the SDQ Parent/Carer on entry compared to 84% at discharge, 62% had difficulties in the high range according to teacher ratings at on entry compared to 58.5% at discharge and of the 33 young people who completed the self rated young persons SDQ, 79% had difficulties in the high range on entry compared to 49% at discharge.

“I can handle awkward situations a bit more; I never used to be able to”

- Children’s Global Assessment Scale (CGAS)

Children’s Global Assessment Scale (CGAS) functioning scores rose from scores in the impaired range to scores in the range of generally functioning pretty well.

Table 8. Graduates Global Assessment Scale on entry and at discharge

| CGAS | T1 n=39 | T4 n=29 |
| --- | --- | --- |
| Mean score | 51.10 | 61.72 |
| Range | 33 - 75 | 33 - 75 |

“The programme has helped me with my peer relationships and at school”

    - High risk behaviours

Young people graduating from the MTFC programme show improvements on all the risk behaviours, except substance abuse, between entering the programme and moving to a new placement.  44.5% of the group of graduates entered the programme with convictions for criminal offences. On leaving the programme only 13% had received a further caution or conviction. Previous history of violent behaviour towards other people reduced from 75% on admission to 46% on leaving the programme. Most young people with a history of self harming behaviour on entry to MTFC-A (30.5%, 49 young people) were no longer engaged in this behaviour on leaving, only 4% (7 young people) did so. Concerns about young people’s sexual behaviour risks to themselves and/or to others reduced during the time in the programme from 49% on entry to 28% on leaving MTFC-A.

Absconding from placements reduced during the time in the programme from 59% on entry to 42.5% on leaving MTFC-A. Incidents of fire setting decreased to 2% from 25% during the placements. Alcohol use reduced from 34% on entry to MTFC to 29.5% during the placement period. Eight of the graduates were known to be using substances on admission to MTFC-A and 10 at discharge. This needs further investigation; it may be that by increasing the supervision of young people more substance use is picked up.

# Figure 12. Summary of High Risk Behaviours at entry and leaving for Graduates

“I don’t get into trouble as much now, I do, but not for serious things”

    - Placement outcomes

# Figure 13. Placement on Discharge for graduates, early leavers and late leavers

53 of the 56 graduates moved to live in either another foster placement (68% n=38), supported lodgings (7% n=4) or returned to their families (20% n=11). The remaining 3 (5%) graduates moved to ‘other’ placements including a mother and baby home unit, bed and breakfast, and specialist therapeutic community. All 11 (100%) of the late leavers went to residential care after leaving MTFC-A. One child who was discharged to a residential educational placement had been admitted at the age of 8 years and stayed in the placement for 2 years and 2 months before discharge.  This was a positive move to a placement that best met his considerable needs after he successfully completed the programme.

The early leavers are a group for whom we might expect to benefit least from the MTFC-A programme (as was found in the OSLC research). Interestingly, over half (58% n=19) of early leavers were discharged to family based placements, 48.5% (n=16) to home or family network and 9.5% (n=3) to foster care. A total of 42% (13) young people left MTFC-A early to go to residential placements, secure unit or to other non-family based placements. There were some gender differences with a higher percentage of boys going home (59%) than girls (36%). Slightly more girls (43%) went to residential units than boys (34%). The early leavers who returned to family placements were all offered follow-up services from their MTFC-A teams.

“I live closer to my family now and I see them much more. I had contact with them once in 2 or 3 years, now I see them four times a year”.

    - Educational outcomes

# Figure 14. Summary of T1 to T4 changes in education factors for graduates

Graduates from the programme showed some improvements on educational factors between admission to and discharge from MTFC-A.  On entry to the programme 46.5% of graduates had a mainstream school placement. This had increased slightly to 50% on leaving the programme. 28.5% of graduates had a placement at a special school on admission to MTFC-A which had risen to 34.5% on leaving. Combined with the figures for mainstream schooling, placements at either mainstream or special school increased from 75% on entry to 84.5% on discharge from the programme. 78.5% of the graduates were reported to have behavioural difficulties at school on entry to the programme. This reduced to 65.5% on leaving the MTFC-A programme. The numbers of children with Special Educational Needs (SEN) statements remained at 47% during placements as did the number of young people (81%) mostly attending their educational resource.

“I don’t get bullied like I used to and my behaviour has got a lot better in school...I haven’t been excluded once”

8.3.5	Leisure outcomes

The last column of figures in Figure 14 above shows the increase in involvement in after school leisure activities for the graduates. On placement 40% were involved in these activities and by discharge this figure had increased to 56%. The MTFC-A programme specifically promotes young people’s involvement in pro-social activities as this has been linked to a reduction in risk for becoming involved in criminal activities.  On leaving the MTFC-A programme 64% of young people were involved in other leisure activities in the community that were not linked to school (sports, youth groups, musical activities etc).

8.3.6	Family and relationship outcomes – The role of the Birth Family Therapist

The key long-term goal for young people is for them to move to a stable, long-term placement. The preference would be for young people to return to their birth families safely. The Birth Family Therapist works alongside parents, coaching them in the effective parenting strategies that have enabled their child to settle into their foster placement. Topics such as encouragement, making effective requests, using routines and diffusing power struggles are covered with lots of opportunity for parents to practise strategies before trying them with their child. The Birth Family Therapist may coach parents in ways to structure contact meetings to become enjoyable for all parties. They will encourage parents to consider their support networks and facilitate them to use these when necessary. The Birth Family Therapist may continue to work with the family once the young person has graduated from their MTFCE foster placement.

Ella (13) had supervised contact with her mum twice yearly and with her maternal grandmother fortnightly. Ella’s grandmother died suddenly and her mum requested that her contact be increased. The Social Worker undertook a piece of assessment work with Ella’s mum and contact was increased. Ella’s mum was very enthusiastic about the parenting work and practised the strategies successfully in the contact sessions. Ella started to ask her mum why she had been abused and why she was looked after. The Birth Family Therapist and Individual Therapist (supervised by the Programme Supervisor) set up some sessions with Ella and her mum, individually and then together, to enable Ella’s mum to give Ella an appropriate understanding of their family history. Ella stays with her mum at weekends and lives with long-term foster carers during the week.

Early in the placement the Birth Family Therapist will investigate whether the preferred option of placement with family members is possible. Many young people who are placed have lost contact with extended family members.  MTFCE Birth Family Therapists will track back through files for mention of family members who may be able to offer placements where return to the birth family is not possible.

Bobby (11) had no contact with his mother since her drug use had prevented her from managing to see him safely. His father’s whereabouts were unknown. Reading the file revealed that he had an aunt in another part of the country with whom he had overnight contact when he was aged between four and seven. The Birth Family Therapist was able to make contact with the aunt and set up regular telephone contact and later, working alongside the Social Worker, overnight contact. This has continued into Darren’s subsequent long-term foster placement.

The Birth Family Therapist will work with any family offering the long-term placement for a young person. The aim of the work is to enable the young person to make the transition from their MTFCE placement. The MTFCE team will have extensive and detailed knowledge of the things that help the young person live successfully in a family and the Birth Family Therapist coaches the new placement in putting this into practice.

8.4	Improving MTFC-A outcomes

There are 56 graduates from 100 young people who have left the MTFC-A programme. The developers at OSLC require 66% of young people to graduate from programmes before programmes can be certified as MTFC providers. Analysis of the MTFC-A data leads to suggestions about ways to increase the number of graduates from the English pilot. The cohort of early leavers is 33 and the cohort of late leavers is 11. The group of late leavers showed the least change in risk taking behaviours from the three cohorts, their offending, violence and self-harming increased during their placement. We would expect around 35% of placements not to lead to graduations and these 11 young people had needs that exceeded the support they could be offered within a foster placement. Their subsequent residential placements offered them a level of support commensurate with their level of need.

We might more usefully look to the early leaver’s cohort for ideas about improving MTFC-A outcomes. These young people showed reductions in risk-taking behaviours which, whilst not as great as for graduates, were improvements on the behaviours they showed on entry to the programme.

    - Targeted extra support for young people with higher disruption rates and lack of school placements

There were some key differences between the early leavers and graduates on entry to MTFC.

Table 9.  Comparisons between Early Leavers and Graduates - No. of Previous Placements and Educational Placements on entry to MTFC-A

|  | Early Leavers n=33 | Graduates n=56 |
| --- | --- | --- |
| No. of Previous Placements: | 0 – 4 5 – 9 10+ | 47% 37% 16% | 56.5% 25.5% 18% |
| Education: | Without a school place No educational provision In full time education In mainstream school or special school Mostly attending educational place | 26% 19.5% 42% 22.5% 50% | 14% 3.5% 69.5% 46.5% 83% |

The early leavers were likely to have had a higher number of previous placements than the graduates with just over a quarter of graduates having 5-9 placements but well over a third of early leavers having 5-9 placements. Both groups had a comparable number of young people who had experienced 10+ placements. The early leavers were almost twice as likely to have no school place when they began their MTFC-A placement as graduates.  Almost a fifth of them (19.5%) had no educational provision at all compared with just 3.5% of graduates when they entered MTFC-A. We know that these two factors; higher number of placement moves and lack of school placements, are predictive of further placement disruption.

It may be useful for the National MTFCE Team to support pilot sites to identify young people at this greater risk for early disruption and for these young people to be offered a higher level of support. There are some good examples of young people being offered educational packages by a combination of MTFC-A team staff and their local Education for Children Looked After teams that could be drawn upon.

8.4.2	Engaging young people with the entire clinical team early in placement

Table 10. Clinical Team contacts during placement for graduates and early leavers

| Regular or some involvement with: | Early Leavers n=33 | Graduates n=56 |
| --- | --- | --- |
| Skills Coach (SC) | 67% | 93.5% |
| Individual Therapist (IT) | 71.5% | 96% |
| Education Worker (EW) | 67% | 89% |
| Family Therapist (FT) | 48% | 74% |

The above table shows the level of involvement young people had with programme staff during placement. Graduates were much more likely to have contact with specific programme staff than early leavers. 67% of early leavers had regular or some contact with the skills coach during their placement compared with 93.5% of graduates. 71.5% of early leavers had regular or some contact with the individual therapist during their placement compared with 96% of graduates. The picture is similar for contact with other key staff; 67% of early leavers had regular or some contact with the education worker during their placement compared with 89% of graduates.  48% of the families of early leavers had regular or some contact with the family therapist during their placement compared with 74% of graduates.

This seems to suggest that the ability of teams to engage young people early in their placement with the entire team could enable young people to complete their individual programmes and go on to graduate.

“My Individual Therapist gives me good advice...tells me how I can deal with situations and how to make them better”.

    - Ensuring young people can make positive choices

Table 11. Early and late leaver’s reasons for leaving MTFC-A

|  | Early Leavers n=33 | Late leavers to non-family placements n=11 |
| --- | --- | --- |
| Young person’s wishes | 14 (45.2%) | 2 (18.2%) |
| Birth family wishes | 2 (6.5%) | 0 (0%) |
| High risk behaviour | 11 (35.5%) | 4 (36.4%) |
| Carer wishes | 1 (3.2%) | 2 (18.2%) |
| Programme completed | 0 (0%) | 2 (18.2%) |
| Other (e.g. breached ASBO) | 3 (9.7%) | 1 (9%) |
| Total | 31 (100%) | 11 (100%) |

When considering ways to improve the outcomes for MTFC-A it is useful to look at the reasons why placements disrupt. Where this is due to young people’s high risk behaviours (including breach of Orders) then this is likely to indicate that this group of young people (19) currently need a higher level of support than can be offered in a family placement. We would expect this group of young people to make up part of the 34% of non-graduates that OSLC would view as acceptable for the MTFC programme.

There are 14 young people in the early leaver group who have chosen to leave their MTFC-A placement. One of these was aged 16, four were aged 15, six were aged 14, one was aged 13 and two aged 11. It may be that young people for whom this is more likely, often those who have experienced several placement moves, could be identified earlier and work could take place with their social workers to help them make the most informed choices possible. The Programme Managers Network is a good forum for sharing ideas about successful communication with Social Workers.

Two of the early leavers left at the wishes of their families. For both of these young people, the MTFC-A teams were able to offer support to their birth families to enable them to remain at home. One team offered a supportive package to a single mother with mental ill-health to enable her to care for her daughter.  She made use of parenting strategies and on-call support offered by the MTFC-A team.

9.	The cost of MTFC-A

9.1	Calculating the costs of MTFC – Loughborough Cost Calculator Project

All the children entering the programme have a history of complex needs, often accompanied by multiple placement breakdown and may be in high cost placements of more than £3000 to £4000 per week or clearly likely to need a high cost placement in the near future. These figures also do not take account of the additional costs of mental health or school support or the costs associated with contacts with the family of origin, travel costs for social workers and so on which may be considerable. In order to assist local teams in calculating the accurate costs of MTFC-A placements compared with supporting a similar young person with complex needs in the care system, the DCSF has commissioned a costing project lead by Professor Harriet Ward and colleagues at Loughborough University. The aim of the project is to calculate the costs incurred over a specific time period to a range of agencies by children who are experiencing MTFC.

This study will directly link with the wider DCSF funded costing programme being undertaken at the Centre for Child and Family Research at Loughborough and would make it possible to include the unit cost of MTFC in future versions of the Cost Calculator for Children’s Services developed by the team.

The costs incurred by a sample of MTFC children are being compared with those incurred by children with similar needs and care histories (but no MTFC placements) for whom the team already hold data collected in the course of earlier costing studies.  Data has been collected on the needs, placements, services provided and outcomes of all children in the sample over a time period to include the year prior to placement in MTFC, during MTFC and where appropriate, subsequent placements. The results of the project will be reported in the autumn and data will be available to teams in advance of, but also add to, the results of the independent evaluation.

Reviews of current residential homes and non-specialist residential care for children and young people with complex needs suggest little in the way of effectiveness. The long-term economic costs of these young people into their twenties and thirties have been estimated at between £500,000 and £2 million per person for extra services in the UK. In contrast evidence regarding this programme in the USA found substantial cost savings over a period of time for this vulnerable group and it is anticipated that MTFCE will also prove cost effective over the longer term. Use of a cost calculator to calculate the realistic costs of a looked after young person compared with the MTFCE programme is likely to be a helpful development for teams needing to make a strong financial case for MTFCE provision in the longer term.

9.2	Comparative costs of MTFC

Current broad calculations of the costs of MTFC, including staffing and overheads, payments to foster carers, travel, accommodation and running costs and expenses suggest that a single MTFC-A placement costs about £1,800 per week based on the recommended minimum of 7 placements and one respite foster carer, depending on local salary, travel and accommodation costs. Costs during the first year when the team is starting up and recruiting  foster carers are greater at about  £2,000 - £2,300 per week per child, based on a start up team of 4 placements plus one respite foster care placement. The nature of the service means that the total costs of recruiting training and supporting foster carers, of intensive 24 hour support for the children and young people, in the placement, at school and in social activities as well as work with their families of origin and/or moving on placements are all included within the costs of the programme. MTFC therefore compares well with specialist services and has the potential to reduce the long term costs for children and young people moving successfully and in a timely manner, through the programme.

Audit data is collected on the costs of the previous placement on entry to MTFC, the cost of the alternative placement if MTFC had not been available and the costs of the follow up placement.

Figure 15.  Weekly cost of previous placement on entry to MTFC-A (n=120)

The available information shows that 36% (43) of the previous placements cost up to £500 per week, 22% (26) cost between £500 and £1500 per week, 19% (23) cost between £1,500 and £2,500 per week, 13% (16) cost between £2,500 and £3,500 per week and 10% (12) exceeded £3,500 a week.

The mean weekly cost of previous placements before MTFC-A was £1509. However, at the time of entering MTFC-A current placements were often breaking down or considered inappropriate and information was gathered on the costs of the anticipated alternative to MTFC-A if a placement had not been available.

Figure 16. Cost of anticipated alternative placement if MTFC had not been available (n=109)

The available information suggested that 19% (21) of the alternative placements would have cost up to £499 per week, 24% (26) would have cost between £500 and £1,499 per week, 16.5% (18) would have cost between £1,500 and £2,499 per week, 23% (25) would have cost between £2,500 and £3,499 per week and 17.5% (19) would have exceeded £3,500 a week. The mean weekly cost of anticipated alternative placements if MTFC had not been available was £2,053.

Based on figures provided by the local MTFC-A teams the predicted costs of the next placement following MTFC was calculated. The table below shows actual weekly costs of the last placement prior to MTFC, the actual costs of the alternative placement if the young person had not come into the programme and the estimated weekly costs of the follow on placement after MTFC for graduates and early leavers.

Table 12.Weekly costs of placements pre and post MTFC

|  | Weekly Cost of previous placement prior to MTFC n= 120 | Weekly cost of alternative placement if MTFC had not been available n=109 | Weekly Cost of placement post MTFC for Graduates n=32 | Weekly Cost of placement post MTFC for Early leavers n= 25 |
| --- | --- | --- | --- | --- |
| Mean | £1509 | £2053 | £392 | £764 |
| Range | £0-£6,000 | £0-£6,000 | £0-£2,000 | £0 - £5,280 |

Mean costs for graduates reduced from £1117 per week to £392. The costs are slightly increased as one of the graduates went to a mother and baby home to work towards independence and a second young person moved to a small independent living unit, both of which cost more than foster care. This represents a mean saving of £725 per week compared to placement on entry and potential savings of up to £1661 per week compared with the anticipated alternative.

As 15 (60%) of the 25 early leavers - for whom we have information - returned home the mean costs for this group are reduced to £764, representing a saving of £1,289 compared with the anticipated alternative placement. However it is likely in view of their complex needs that some of these children will come back into the care system from their families. The mean cost of placements post MTFC for early leavers – not including those who returned home - was £1,910. Follow up of all these groups for a further year post placement in MTFC-A will be helpful in assessing whether the changes and resultant cost savings have been maintained.

10.	Foster Carers in Multidimensional Treatment Foster Care – England

To date the audit data collected by the MTFCE National Implementation Team has focused on the young people placed in the programme.  More recently, and in recognition of their central importance in the programme, we have begun to collect some audit data on the foster carers and to interview them about their views on MTFCE. This audit is at a very early stage and we expect to report much more fully in the 2009 Project Report.

10.1	Foster Carer Audit

To date completed forms have been collected for 56 foster carers out of a total of approximately 70 carers currently caring for, or available for, an MTFC-Adolescent placement.  The audit data for these 56 carers are as follows:

- The carers range in age from 30 to 65 years old with the majority being aged between 45 and 56.  78.6% are female (n=44) and 80% are either married or cohabiting.  10.9% are single and 9.1% are divorced or separated.  They are predominantly from a white British background (76.5%) with 7.3% being black British and another 7.3% black Caribbean and the remainder being Asian or from other white backgrounds

- Most of the 56 carers surveyed have grown up birth children (87.3%), with  some of the grown up children  living  at home either some or all of the time (n=12).

- 22.6% of the carers had previously fostered (n=12), 8 of these had fostered between 1 and 9 children and 4 of them had fostered between 35 and 100 children. To date most of the 56 carers have taken either one or two placements.  Two carers have had 4 placements and one has had 9.

This audit data will be systematically collected and updated for all of the MTFC-Adolescent programme foster carers providing  some simple demographic information on all of the foster carers as well as the ability to track the number of placements they take, the outcome of these placements and the reasons for their ceasing to foster with MTFCE (where applicable).  We hope to gather sufficient data to report some meaningful findings in the above areas within the next 12 months.  There are also plans to extend the foster carer audit to the Prevention (3 to 6) and Childhood (7 to 11) programmes.

10.2	Foster Carers’ Views of MTFC Interview

A semi-structured interview covering all the dimensions of the model has been developed by the National Team based on some research carried out by the Swedish MTFC programme.  To date interviews have been conducted by the National Team assistant psychologist with 12 carers.  The interviews are video recorded and transcribed for subsequent content analysis. The views expressed so far have been overwhelmingly positive regarding the model with very few criticisms or suggestions for changing or improving the model. A sample of the views expressed in response to some of the questions in the 6 interviews that have been transcribed so far are presented here.

- What is your experience so far of MTFCE?

“Well excellent, especially for me because I like the structure of the programme...  I don’t think I could have just been a traditional foster carer because I like the discipline of the points and levels, it keeps me on track too.  I think it’s a really good system, it works really well and I love the fact that it avoids all conflict with the youngsters...

- How did you find the training?

“The training was just brilliant.  It was really, really informative.  It was quite different from other training I’ve done, …because it was specific with the information provided.

- How do you find the points and levels system?

“Well in the beginning getting into the points, the point system is about the most difficult part.  You know, you got to try not to be punitive, you got to look not so much at the negatives but look at the positives, I think I’ve cracked that now.  If he’s had a particularly bad day at school I always look for …the point where’s he’s had…(pause) a good moment and I will give him extra points for that.

- How useful do you find the Parent Daily Report?

“Very, very useful. Because when you go through it ..looking at all the behaviours it does then give you an idea of which behaviours you need to work on.  My first placement, she had the most disgusting habit of spitting and it was the first thing we targeted, the spitting and the swearing and within the first 3 or 4 weeks no spitting.  I’ve never seen her spit again.”

- How have you found the 24/7 cover?

“Really helpful, especially at really difficult times.  Sometimes it’s even if you want to check ‘have I done this right’ and it’s nice to know that you can make contact with whoever is on duty and they’ll say yes or try it this way and I think that’s really helpful”

- What do you think about the foster carer meetings?

“Oh, they’re really useful.  It’s nice to know you can sit down once a week and share everything with other carers.  Especially if you’re having a difficult time it’s nice to hear the other carers say “yes I’m having a difficult week as well” and you think “it’s not just me” We can share information and get ideas from each other.  Yes we have the team for support but there’s nothing better than another foster carer to sit and chat to and give you ideas or give you support.  Because they’re doing the job, they’re doing exactly what we’re doing and we’re all in it together.”

- What qualities do you need to be an effective MTFC carer?

“You need to be clear.  You need to be understanding; you definitely need a sense of humour.  You need to be resilient.”

“Relaxed, calm, resilient.  Comfortable with yourself, I don’t think you can be too self-doubting, you need to feel fairly confident that you are your own person.  The kids work hard sometimes to try to make you feel that you’re worse than dirt, you know and you’ve got to feel comfortable with yourself to think that actually, “no I’m not”, so a bit of self confidence, self esteem.  I think you need to be quite warm, and friendly and easy going (long pause) and have a sense of humour, you’ve got to see the humour in it...”

11.	Consultation with Oregon Social Learning Center

The National Team have continued to work closely with TFC Consultants in Oregon and receive clinical telephone consultation with Dr Peter Sprengelmeyer on the operational aspects of the MTFC-A model. This alternates with consultation from Dr Kim Bronz on the development and implementation of the MTFC-P model. TFC Consultants have also regularly joined with the National Team to deliver training in both the MTFC-A and MTFC-P models to clinical team staff and new foster carers. Consultation includes video review of tapes provided by the programme sites of clinical meetings, foster carer meetings and MTFC-P children’s groups for the monitoring of fidelity to the programme and consultation on the consultation provided to the sites by the National Team.

12.	Network Partnership

The National Implementation Team have now formally signed an agreement to become the UK Network Partner with TFC Consultants in Oregon, USA enabling us to provide implementation services, training and consultation in the MTFC-A programme for new teams wishing to develop the model in the UK outside the DCSF funded programme. There are 10 existing English teams who have contracted for further services to prepare them for applying for MTFC Certification. This is an important development which will make a considerable contribution to sustaining programmes and rolling out further programmes over the next few years.

13.	Intensive Fostering

In 2004 the Youth Justice Board decided to use the same model of MTFC with the Intensive Fostering Programme for young offenders serving a community based sentence. Three pilot programmes have successfully been established. DCSF and the National Team are working in close collaboration with the YJB senior manager and lead consultant. YJB staff and their site consultant have previously joined the MTFCE clinical staff training and have conducted joint training of new foster carers in conjunction with National Team staff. Opportunities for further close collaboration between MTFCE and the YJB are currently being negotiated.

14.	The Learning So Far

14.1	Learning from the treatment model

Over the last 4 years the national MTFCE programme has been developing a sound body of knowledge about what does and doesn’t work and this year’s audit analysis has begun to confirm some of the ideas from the local and National Team staff about successful implementation. (Please also see “The Learning So Far” in the three previous annual reports for more details).

It is clear that working with young people with the level of difficulties that those coming into the MTFCE programme present requires sustained effort and tenacity in addition to the structured framework offered by the MTFC model. However, there are several aspects of the model which, when delivered consistently, combine to produce optimum outcomes for young people:

- Quality observations allow for the complexity of young people’s presentations to be understood; to see when aggressive behaviours are being driven by anxiety or to see the impact of a young person’s impulsiveness on their conduct problems in school. This level of observation allows interventions to be designed that address the functions of the behaviour as well as the behaviour itself.  MTFC foster carers are trained to contribute such observations.

- A developmental perspective is essential to enable teams to position the young person in relation to the skills they need to acquire. The teaching of new skills in MTFC programmes is set within such a developmental framework.

- Maintaining a positive focus is crucial; being positive about the small steps that a young person is taking and also about the way these steps contribute to longer term goals for the young person and their family. This is emphasised within the structure of the MTFC model.

- The ecological application of interventions enables young people to experience success with their targets across many dimensions; individually, in their foster home, at school, with their birth families and with their peers. These interventions are supported by the different team members to maximise opportunities for success.

- For teams, having a common language has enabled them to channel professional expertise into the helping task. Teams are involved in learning the language of the model during their training and are encouraged to ‘translate’ previously learned ideas into MTFC language to provide the most complete service to the children and young people they work with.

- Foster carer recruitment is a continual process. There are now teams across England who have highly trained and experienced foster carers who are able to support newer carers coming on board. Carers consistently tell us that the support from other carers is the most useful aspect of the MTFC programme.

14.2	Learning from the implementation process

In addition to the learning about what works clinically we are increasing our knowledge about what is needed to implement and maintain evidence based programmes and the importance of the implementation process and system structures in creating success. We know that the programme works best when it adds to and complements existing robust provision for looked after children. The introduction of a new fostering service has encouraged local authorities to examine their range of provision and increase the clarity of function of each aspect. A number of existing sites have developed tiered fostering services into which MTFC fits as a specialist service (for example they may have mainstream provision, specialist long-term provision, intensively supported long-term provision and MTFC). Two MTFC-A sites have developed complementary long-term fostering schemes for children moving out of MTFC as a means of resolving the ongoing difficulty of finding suitable follow-on placements. These are new developments for these local authorities and continue to provide some support to both young people and foster carers. One team has its MTFC service sitting alongside multi-agency residential and fostering provision for young people, including those with complex mental health needs (including psychosis and self-harm). Having senior managers who have budgetary and managerial responsibilities, are champions for the programme and innovators of service development continues to be important. There are two local authorities, Dudley and Solihull, who have successfully bid for all three MTFC programmes and are developing services with partner agencies.

It remains clear that evidence based programmes such as MTFCE are not self-sustaining and without continuing support natural model drift would occur with the resulting reduction of model adherence and outcomes. National programmes in particular, where coherence of approach and shared learning are important aims, depend on having a system in place for monitoring implementation progress, training and access to ongoing support in the implementation of the main tools of the programme. Long-term continuation of MTFC in England will hopefully be sustained through the development of the Network Partnership with Treatment Foster Care associates in Oregon.

15.	Current Challenges

15.1	Planning for long term placements post MTFC

The introduction of short-term ‘treatment’ fostering provision requires local authorities to examine their current practise within fostering. Most MTFC teams report difficulties moving children on in a planned way. The following example is not unusual:

Dean (12) had moved into an MTFCE placement exhibiting multiple problem behaviours, including aggression, hyperactivity and emotional withdrawal.  He had been excluded from his special school and had no contact with family members due to his behavioural difficulties. After 14 months in an MTFCE placement his behaviours on the PDR were reduced to 2-3 each day, he had re-established himself in school and was having regular contact with three family members. The MTFCE team asked the fostering team for a permanent single placement for him and gave three months for this to be achieved. The fostering service advertised and recruited a couple to care for Dean. However, they used the placement for another ‘emergency’ placement. Dean is asking why he has not moved on and his behaviours have deteriorated.

‘Dean’ is one of an increasing number of young people in the MTFCE Project whose achievements are being compromised by a lack of planning within the wider fostering service. The matching of children and young people is viewed as an intrinsic and crucial aspect of fostering practise yet we see little evidence of this in some local authorities, where placements are made using urgency as sole criteria. Two MTFC teams (Solihull and Salford) have set up additional teams to provide long-term placements for young people post MTFC and for other young people needing a higher level of support. One team (Hammersmith and Fulham) is fortunate enough to have a permanence planning team working alongside them who see the long-term value in matching young people for permanent placements. However, these examples are the exception rather than the norm. If we are to improve placement stability and outcomes for young people then we need to address the way in which placements are allocated.

15.2	Recruitment and Retention of Foster Carers

MTFC programmes seem to retain carers well. This will be tracked more closely in the coming year with the Foster Carer audit. However, it is apparent that the recruitment of foster carers is easier in some areas of England than others. The MTFC programme brings Foster Carer Recruiters together to share their practise about the best ways to recruit carers. Some teams are looking to join together to run regional recruitment campaigns which may address recruitment difficulties in specific regions.

15.3	Independent Evaluation

The use of randomisation in making placements has proved challenging for most local authorities. However, the three teams in the fourth round of MTFC-A are randomising each of their placements and teams from previous rounds have made a commitment to do so.

The National Team supports project teams and the independent evaluators in ensuring the national evaluation proceeds as smoothly as possible.

16.	Aims for the Next Year

16.1	Audit Data

The National Team will continue to collect data to assist with planning and internal monitoring of the MTFCE Pilot. Data will be collected on young people; their characteristics, outcomes and programmes. A database has been set up for collecting similar information on children placed in MTFC-P and a database for the MTFC-C programme is planned. In addition the foster carer audit will be expanded to include carers from the MTFC-P and MTFC-C programmes.

16.2 Programme Fidelity

The National Team will need to continue to monitor and support teams to adhere to the three MTFCE models in order to secure the best outcomes for children and young people and to support those in preparing and applying for certification as MTFC sites.

16.3 Training and Support

The National Team will need to ensure that training, networking and developmental needs of teams in the programme are met within an appropriate time period and within current resources. Teams within the Network Partnership agreement will need to decide on their next steps after the end of the current contract in March 2009.

# Appendix 1

# Multidimensional Treatment Foster Care in England (MTFCE) Project Staffing

The MTFC programme for adolescents and the MTFC-P programme for 3-6 year olds, developed by the Oregon Social Learning Center in the USA, provides clear guidelines for the staffing of the clinical team which is essential for carrying out the treatment programme in the most effective, consistent and coherent way. This is important in order to ensure fidelity to the model and the greatest chance of positive outcomes for the children and young people admitted to the programme.

The multi-agency MTFC team therefore consists of staff from social services, CAMHS and education to meet these requirements and the requirements of our specific context in England.

MTFC-A Staffing Requirements

### Programme Manager

- Programme Supervisor

- Foster Carer recruiter/trainer

- Birth Family Therapist

- Young Person’s Individual Therapist

- Skills Coach

- Education personnel e.g. teacher

- Psychiatrist (1-2 sessions)

- Clinical Psychologist (if not appointed as PS or IT then 1-2 sessions for assessment)

MTFC-P Staffing Requirements

### Programme Manager

### Programme Supervisor

### Foster Carer recruiter/supervisor

### Birth Family Therapist

### Children’s Group Lead Teacher/Skills Coach

### Skills Coach

MTFC-C Staffing Requirements

### Programme Manager

### Programme Supervisor

### Foster Carer recruiter/ supervisor

### Birth Family Therapist

### Skills Coach

### Education personnel e.g. teacher

Appendix 2

# MTFC for Adolescents Points and Levels System

During a young person’s MTFC placement they gradually progress through a three level behaviour management system.  This is a structured programme designed to teach pro-social skills, reinforce positive behaviour and attitudes through tangible rewards and offer sanctions for problem behaviour.  The young person moves up to the next level by earning sufficient points.  Each successive level is characterised by increased autonomy and an increase in privileges. The focus is on being positive, developing a mentoring relationship with foster carers, and helping young people to be successful and develop new skills. The aim is to have a young person functioning well within the context of a family by the end of the placement.

Level 1

The young person spends a minimum of 3 weeks at Level 1 when they first enter the placement and are settling in.  At this level they are supervised at all times by their carers, education staff and other MTFC workers. Young people are given immediate reinforcement for appropriate behaviour which may have been ignored in the past. Points are earned easily for routine activities, for example - getting up on time would earn 10 points. Typically, young people earn 100 to 130 points a day. They must accumulate a total of 2,100 points to move to Level 2, which most do in about 3 weeks. The points are traded for very basic privileges the following day, for example - watching a TV programme.

Level 2

The treatment team is likely to see the greatest change in the young person’s behaviour during Level 2.  Points earned one week are used to buy privileges the next. The young person begins to experience delayed gratification and to develop the capacity to plan ahead. The amount and quality of privileges increases from Level 1 and can continue to increase throughout Level 2 as the young person’s skills improve, offering an opportunity to become increasingly more responsible and confident.

Young people can use points to choose to stay up later, have longer time on the computer, activity time with friends - although the carers and MTFC team will know where a young person is at any time. They can be demoted to Level 1 for a day if they fail to earn the minimum amount of daily points. The therapist works with the young person to propose new privileges that are of interest to her. She is then coached on how to appropriately ask and negotiate for what she wants. Typically youngsters earn 700 to 900 points per week on Level 2, and stay on this level for 12 to 16 weeks.

Level 3

Level 3 can be considered a maintenance phase.  During this time, young people are expected to maintain their newly learned skills with less structure.  Youngsters have more opportunity to exercise their own judgment and must handle that responsibility reasonably well to stay on this level. The programme supervisor and foster carers use their discretion on this level to customise privileges as well as expected behaviours, being careful to not allow more freedom than the young people can handle, but also being sure they have opportunities to practice appropriate skills and behaviours in more naturalistic settings.  To remain at this level a minimum of 120 points must be earned each day.

Basic privileges no longer need to be earned and encouragement is given to take greater responsibility for their own decision-making and actions.  However, plans for free time must still be approved in advance. Positive achievements and pro-social interactions are consolidated during Level 3. Plans for any aftercare placement are arranged to fit with these achievements to minimise transition difficulties.

Appendix 3

Key:	Solid line	 = directly works with young person as appropriate

Dotted line	 = indirectly works with young person

The above is an example of the co-ordination of work around a young person who has difficulties in a number of areas including; absconding, outbursts, rudeness, non-cooperation, self-care and hygiene, making and keeping friends, confidence and self–esteem. The treatment programme is mediated through the foster carer and is supported by the work of the team in their distinct roles. The Programme Supervisor conducts and directs the clinical team staff in a co-ordinated manner which allows several people to be working on a specific difficulty at one time and in different but complementary ways.

Appendix 4

NSW Department of Health – MH-OAT Project 	CGAS Information Sheet

Version 1.0 31/05/2002 Page 1 of  2

Children’s Global Assessment Scale (CGAS)

1. Enter a score from 1-100

2. Rate the child/adolescents most impaired level of general functioning during the period rated by selecting the lowest level which describes his/her functioning on a hypothetical continuum of health-illness

3. Use intermediary levels e.g. 35, 94, 68

4. Rate actual functioning regardless of treatment or prognosis, using the descriptions below as a guide

100-91 	Superior functioning

90-81 		Good functioning

80-71 		No more than a slight impairment in functioning

70-61 		Some difficulty in a single area, but generally functioning pretty well

60-51 		Variable functioning with sporadic difficulties

50-41 		Moderate degree of interference in functioning

40-31 		Major impairment to functioning in several areas

30-21 		Unable to function in almost all areas

20-11 		Needs considerable supervision

10-1 		Needs constant supervision

Principle reference

Schaffer D, Gould MS, Brasic J, et al. (1983) A children's global assessment scale (CGAS).

Archives of General Psychiatry, 40, 1228-1231.

Description

The Children’s Global Assessment Scale (CGAS) is a measure developed by Schaffer and colleagues at the Department of Psychiatry, Columbia University to provide a global measure of level of functioning in children and adolescents. The measure provides a single global rating only, on scale of 0-100. In making their rating, the clinician makes use of the glossary details to determine the meaning of the points on the scale.

CGAS Glossary

Rate the patient’s most impaired level of general functioning for the specified time period by selecting the lowest level which describes his/her functioning on a hypothetical continuum of health-illness. Use intermediary levels (e.g. 35, 58, 62).

Rate actual functioning regardless of treatment or prognosis. The examples of behaviour provided are only illustrative and are not required for a particular rating.

NSW Department of Health – MH-OAT Project CGAS Information Sheet

Version 1.0 31/05/2002 Page 2 of 2

100-91 Superior functioning in all areas (at home, at school and with peers); involved in a wide range of activities and has many interests (e.g., has hobbies or participates in extracurricular activities or belongs to an organised group such as Scouts, etc); likeable, confident; ‘everyday’ worries never get out of hand; doing well in school; no symptoms.

90-81 Good functioning in all areas; secure in family, school, and with peers; there may be transient difficulties and ‘everyday’ worries that occasionally get out of hand (e.g., mild anxiety associated with an important exam, occasional ‘blowups’ with siblings, parents or peers).

80-71 No more than slight impairments in functioning at home, at school, or with peers; some disturbance of behaviour or emotional distress may be present in response to life stresses (e.g., parental separations, deaths, birth of a sib), but these are brief and interference with functioning is transient; such children are only minimally disturbing to others and are not considered deviant by those who know them.

70-61 Some difficulty in a single area but generally functioning pretty well (e.g., sporadic or isolated antisocial acts, such as occasionally playing hooky or petty theft; consistent minor difficulties with school work; mood changes of brief duration; fears and anxieties which do not lead to gross avoidance behaviour; self-doubts); has some meaningful interpersonal relationships; most people who do not know the child well would not consider him/her deviant but those who do know him/her well might express concern.

60-51 Variable functioning with sporadic difficulties or symptoms in several but not all social areas; disturbance would be apparent to those who encounter the child in a dysfunctional setting or time but not to those who see the child in other settings.

50-41 Moderate degree of interference in functioning in most social areas or severe impairment of functioning in one area, such as might result from, for example, suicidal preoccupations and ruminations, school refusal and other forms of anxiety, obsessive rituals, major conversion symptoms, frequent anxiety attacks, poor to inappropriate social skills, frequent episodes of aggressive or other antisocial behaviour with some preservation of meaningful social relationships.

40-31 Major impairment of functioning in several areas and unable to function in one of these areas (i.e., disturbed at home, at school, with peers, or in society at large, e.g., persistent aggression without clear instigation; markedly withdrawn and isolated behaviour due to either mood or thought disturbance, suicidal attempts with clear lethal intent; such children are likely to require special schooling and/or hospitalisation or withdrawal from school (but this is not a sufficient criterion for inclusion in this category).

30-21 Unable to function in almost all areas e.g., stays at home, in ward, or in bed all day without taking part in social activities or severe impairment in reality testing or serious impairment in communication (e.g., sometimes incoherent or inappropriate).

20-11 Needs considerable supervision to prevent hurting others or self (e.g., frequently violent, repeated suicide attempts) or to maintain personal hygiene or gross impairment in all forms of communication, e.g., severe abnormalities in verbal and gestural communication, marked social aloofness, stupor, etc.

10-1 Needs constant supervision (24-hour care) due to severely aggressive or self-destructive behaviour or gross impairment in reality testing, communication, cognition, affect or personal hygiene

# Footnotes

Koprowska J & Stein M (2000) The Mental Health of ‘Looked-after’ Young People. In P Aggleton, J Hurry & I Warwick (Eds) Young People and Mental Health. London: John Wiley & Sons Ltd.

Henggeler, S. W., Melton, G. B., Brondino, M. J., Scherer, D. G., Hanley, J. H. (1997) Multisystemic Therapy With Violent and Chronic Juvenile Offenders and Their Families: The Role of Treatment Fidelity in Successful Dissemination. Journal of Consulting and Clinical Psychology, 65: 831-833.

Scott, S, Carby A, Rendu A (2007) Impact of therapist skill on outcomes of parenting programs for child antisocial behaviour. Submitted

Statistics in Education, Children looked after in England (including adoption and care leavers) year endings March 2007, Statistical First Release Office of National Statistics, 2007.

Statistics in Education, Outcome indicators for Children Looked After: twelve months to 30 September 2007, England, Statistical First Release Office of National Statistics, 2008

ONS Survey

Statistics in Education, Outcome Indicators for Looked After Children, Twelve months to 30 September 2006, England, Statistical First Release Office of National Statistics (2007).

# Text boxes

National Team Staff

Executive Director – Stephen Scott, Professor in Child Health & Behaviour,

Consultant Child & Adolescent Psychiatrist

Project Director - Rosemarie Roberts, Consultant Systemic Therapist

Site Consultants

North Team- Booth Hall Children’s Hospital, Manchester	            South Team - Maudsley Hospital, London

Project Manager- Dawn Walker – Consultant Systemic Therapist (f/t)   Cath Connolly – Systemic Therapist (p/t)

Frances Gulliford – Consultant Clinical Psychologist (p/t)		Nicola Cosgrave – Clinical Psychologist (p/t)

Colin Waterman–  Systemic Therapist (f/t)				Brigitte Wilkinson – Clinical Psychologist (p/t)

Kate Friedmann – Clinical Psychologist (p/t)				Megan Jones – Clinical Psychologist (f/t)

Helen Morley – Assistant Psychologist (p/t)				Tom Allen – Assistant Psychologist (f/t)

Reina Yaidoo – Team Administrator (p/t)				Ineke Burke – Senior Administrator (f/t)

Fiona Taylor – Administrator

OSLC + National Team train Clinical staff in specific MTFCE model

Appoint staff required by each programme eg Lead Skills Coach and BFT for MTFC-P

Appoint

Skills

Coach

Appoint Project

Manager & Foster

Carer Recruiter

Appoint Programme Supervisor

Referrals accepted, child/YP seen, consents obtained

Individual programme devised

Assessment training

Set up admin procedures – referral criteria, pathways

Assessments of child/YP, approval & matching

Plan for sustainability

Goals & Tasks of Team defined

Identify accommodation

Networking & stakeholder presentations on MTFC Programme

Inter-agency structures in place

Agree & sign off JD’s for first posts

First

Placement

Recruitment programme leaflets & posters

Training of Foster carers by OSLC + National Team in MTFC model

Approval by panel

Assessment plus

“Skills to Foster” Course

Telephone interview & home visits

Recruit Foster Carers

<4 week time gap

Continue recruitment of Foster Carers